## Summary
Sr. No. | Item Description | Weighatge for the project
1 | Preliminaries | 1%
2 | Design | 2.986%
3 | Procurement | 15.97%
4 | Construction | 75.07%
5 | T&C | 4.971%
| Total | 100%

## Working
PART-A: COST OF BUILDING WORKS (Fully facilitated as per Scope, Design Basis
[5 empty] | Weightage for the Item |  |  |  |  | Weighatge Building Wise |  |  |  |  | Weighatge for the project
Sr. No. | ITEM DESCRIPTION | Procurement Items Considered | Overall Weightage | % breakup | Preliminaries | Design | Procurement | Construction | T&C | Preliminaries | Design | Procurement | Construction | T&C | Preliminaries | Design | Procurement | Construction | T&C | Sum | Price Bid Value INR (Crore)
1) | Exhibition Hall No. 1 |  | 12.2% | [17 empty] | 340.4401
a) | Civil works including structural steel, roofing complete | Str. Steel, Roofing |  | 42.87% | 1% | 2% | 10% | 85% | 2% | 0.4287% | 0.8575% | 4.287% | 36.44% | 0.8575% | 0.0523% | 0.1046% | 0.523% | 4.445% | 0.1046% | 5.23% | 145.9615
b) | Internal Finishing including Acoustics and Special Finishes complete | = |  | 24.44% | 1% | 2% |  | 94% | 3% | 0.2444% | 0.4889% | 0% | 22.98% | 0.7333% | 0.02982% | 0.05963% | 0% | 2.803% | 0.08945% | 2.982% | 83.2149
c) | External Finishes including Façade, Special Finishes | = |  | 6.447% | 1% | 2% |  | 95% | 2% | 0.06447% | 0.1289% | 0% | 6.125% | 0.1289% | 0.007864% | 0.01573% | 0% | 0.7471% | 0.01573% | 0.7864% | 21.9482
d) | Plumbing works | = |  | 0.8714% | 1% | 5% |  | 84% | 10% | 0.008714% | 0.04357% | 0% | 0.732% | 0.08714% | 0.001063% | 0.005315% | 0% | 0.08929% | 0.01063% | 0.1063% | 2.9668
e) | Electrical works | Solar PV Systems |  | 3.932% | 1% | 5% | 18% | 66% | 10% | 0.03932% | 0.1966% | 0.7077% | 2.595% | 0.3932% | 0.004796% | 0.02398% | 0.08633% | 0.3165% | 0.04796% | 0.4796% | 13.3856
f) | Lift, Escalators & travellators | VHT |  | 0.9378% | 1% | 2% | 90% | 2% | 5% | 0.009378% | 0.01876% | 0.844% | 0.01876% | 0.04689% | 0.001144% | 0.002288% | 0.103% | 0.002288% | 0.005719% | 0.1144% | 3.1926
g) | HVAC works | Chiller, AHU, V Fans, TFA |  | 3.384% | 1% | 5% | 18% | 66% | 10% | 0.03384% | 0.1692% | 0.609% | 2.233% | 0.3384% | 0.004127% | 0.02064% | 0.07429% | 0.2724% | 0.04127% | 0.4127% | 11.519
h) | Firefighting works | = |  | 2.538% | 1% | 5% |  | 84% | 10% | 0.02538% | 0.1269% | 0% | 2.132% | 0.2538% | 0.003096% | 0.01548% | 0% | 0.26% | 0.03096% | 0.3096% | 8.64
i) | ICT, AV system, Security & Surveillance | = |  | 10.41% | 1% | 5% |  | 84% | 10% | 0.1041% | 0.5203% | 0% | 8.74% | 1.041% | 0.01269% | 0.06346% | 0% | 1.066% | 0.1269% | 1.269% | 35.4233
j) | Lighting | = |  | 4.168% | 1% | 2% |  | 92% | 5% | 0.04168% | 0.08335% | 0% | 3.834% | 0.2084% | 0.005084% | 0.01017% | 0% | 0.4677% | 0.02542% | 0.5084% | 14.1884
k) | Misc. works | = |  | 0% | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0
| SUB TOTAL 1 | = |  | 100%
2) | Exhibition Hall No. 2 |  | 10.3% | [17 empty] | 287.4552
a) | Civil works including structural steel | Str. Steel, Roofing |  | 48.11% | 1% | 2% | 10% | 85% | 2% | 0.4811% | 0.9622% | 4.811% | 40.89% | 0.9622% | 0.04955% | 0.0991% | 0.4955% | 4.212% | 0.0991% | 4.955% | 138.2892
b) | Internal Finishing including Acoustics and Special Finishes | = |  | 23.39% | 1% | 2% |  | 94% | 3% | 0.2339% | 0.4678% | 0% | 21.99% | 0.7017% | 0.02409% | 0.04818% | 0% | 2.265% | 0.07227% | 2.409% | 67.2389
c) | External Finishes including Façade, Special Finishes | = |  | 8.1% | 1% | 2% |  | 95% | 2% | 0.081% | 0.162% | 0% | 7.695% | 0.162% | 0.008343% | 0.01669% | 0% | 0.7926% | 0.01669% | 0.8343% | 23.2853
d) | Plumbing works | = |  | 0.926% | 1% | 5% |  | 84% | 10% | 0.00926% | 0.0463% | 0% | 0.7778% | 0.0926% | 0.0009537% | 0.004769% | 0% | 0.08011% | 0.009537% | 0.09537% | 2.6618
e) | Electrical works | Solar PV Systems |  | 4.342% | 1% | 5% | 18% | 66% | 10% | 0.04342% | 0.2171% | 0.7815% | 2.866% | 0.4342% | 0.004472% | 0.02236% | 0.08049% | 0.2951% | 0.04472% | 0.4472% | 12.4811
f) | Lift, Escalators & travellators | VHT |  | 1.499% | 1% | 2% | 90% | 2% | 5% | 0.01499% | 0.02998% | 1.349% | 0.02998% | 0.07495% | 0.001544% | 0.003088% | 0.139% | 0.003088% | 0.00772% | 0.1544% | 4.3091
g) | HVAC works | Chiller, AHU, V Fans, TFA |  | 4.621% | 1% | 5% | 18% | 66% | 10% | 0.04621% | 0.231% | 0.8317% | 3.05% | 0.4621% | 0.004759% | 0.02379% | 0.08566% | 0.3141% | 0.04759% | 0.4759% | 13.2824
h) | Firefighting works | = |  | 2.328% | 1% | 5% |  | 84% | 10% | 0.02328% | 0.1164% | 0% | 1.955% | 0.2328% | 0.002397% | 0.01199% | 0% | 0.2014% | 0.02397% | 0.2397% | 6.6906
i) | ICT & AV system | = |  | 4.852% | 1% | 5% |  | 84% | 10% | 0.04852% | 0.2426% | 0% | 4.076% | 0.4852% | 0.004997% | 0.02499% | 0% | 0.4198% | 0.04997% | 0.4997% | 13.9473
j) | Lighting | = |  | 1.833% | 1% | 2% |  | 92% | 5% | 0.01833% | 0.03666% | 0% | 1.687% | 0.09166% | 0.001888% | 0.003776% | 0% | 0.1737% | 0.00944% | 0.1888% | 5.2695
k) | Misc. works | = |  | 0% | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0
| SUB TOTAL 2 | = |  | 100%
3) | Foyer including Basement in front of Exhibition Hall No. 1 |  | 8.304% | [17 empty] | 231.7553
a) | Civil works including structural steel | Str. Steel, Roofing |  | 59.84% | 1% | 2% | 10% | 85% | 2% | 0.5984% | 1.197% | 5.984% | 50.86% | 1.197% | 0.04969% | 0.09938% | 0.4969% | 4.224% | 0.09938% | 4.969% | 138.6846
b) | Internal Finishing including Acoustics and Special Finishes | = |  | 16.27% | 1% | 2% |  | 94% | 3% | 0.1627% | 0.3253% | 0% | 15.29% | 0.488% | 0.01351% | 0.02701% | 0% | 1.27% | 0.04052% | 1.351% | 37.6976
c) | External Finishes including Façade, Special Finishes | = |  | 7.368% | 1% | 2% |  | 95% | 2% | 0.07368% | 0.1474% | 0% | 7% | 0.1474% | 0.006118% | 0.01224% | 0% | 0.5812% | 0.01224% | 0.6118% | 17.0755
d) | Plumbing works | = |  | 0.1504% | 1% | 5% |  | 84% | 10% | 0.001504% | 0.00752% | 0% | 0.1263% | 0.01504% | 0.0001249% | 0.0006245% | 0% | 0.01049% | 0.001249% | 0.01249% | 0.34857
e) | Electrical works | Solar PV Systems |  | 2.965% | 1% | 5% | 18% | 66% | 10% | 0.02965% | 0.1482% | 0.5336% | 1.957% | 0.2965% | 0.002462% | 0.01231% | 0.04431% | 0.1625% | 0.02462% | 0.2462% | 6.8707
f) | Lift, Escalators & travellators | VHT |  | 1.416% | 1% | 2% | 90% | 2% | 5% | 0.01416% | 0.02831% | 1.274% | 0.02831% | 0.07078% | 0.001175% | 0.002351% | 0.1058% | 0.002351% | 0.005877% | 0.1175% | 3.2806
g) | HVAC works | Chiller, AHU, V Fans, TFA |  | 4.007% | 1% | 5% | 18% | 66% | 10% | 0.04007% | 0.2003% | 0.7213% | 2.645% | 0.4007% | 0.003327% | 0.01664% | 0.05989% | 0.2196% | 0.03327% | 0.3327% | 9.2864
h) | Firefighting works | = |  | 2.516% | 1% | 5% |  | 84% | 10% | 0.02516% | 0.1258% | 0% | 2.114% | 0.2516% | 0.002089% | 0.01045% | 0% | 0.1755% | 0.02089% | 0.2089% | 5.8317
i) | ICT & AV system | = |  | 4.692% | 1% | 5% |  | 84% | 10% | 0.04692% | 0.2346% | 0% | 3.941% | 0.4692% | 0.003896% | 0.01948% | 0% | 0.3273% | 0.03896% | 0.3896% | 10.8733
j) | Lighting | = |  | 0.7794% | 1% | 2% |  | 92% | 5% | 0.007794% | 0.01559% | 0% | 0.717% | 0.03897% | 0.0006472% | 0.001294% | 0% | 0.05954% | 0.003236% | 0.06472% | 1.8062
k) | Misc. works | = |  | 0% | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0
| SUB TOTAL 3 | = |  | 100%
4) | Foyer including Basement in front of Exhibition Hall No. 2 |  | 8.483% | [17 empty] | 236.7494
a) | Civil works including structural steel | Str. Steel, Roofing |  | 56.59% | 1% | 2% | 10% | 85% | 2% | 0.5659% | 1.132% | 5.659% | 48.1% | 1.132% | 0.048% | 0.096% | 0.48% | 4.08% | 0.096% | 4.8% | 133.9662
b) | Internal Finishing including Acoustics and Special Finishes | = |  | 18.42% | 1% | 2% |  | 94% | 3% | 0.1842% | 0.3683% | 0% | 17.31% | 0.5525% | 0.01562% | 0.03124% | 0% | 1.468% | 0.04687% | 1.562% | 43.6006
c) | External Finishes including Façade, Special Finishes | = |  | 10.13% | 1% | 2% |  | 95% | 2% | 0.1013% | 0.2026% | 0% | 9.621% | 0.2026% | 0.008591% | 0.01718% | 0% | 0.8161% | 0.01718% | 0.8591% | 23.977
d) | Plumbing works | = |  | 0.04233% | 1% | 5% |  | 84% | 10% | 0.0004233% | 0.002116% | 0% | 0.03555% | 0.004233% | 3.59e-05% | 0.0001795% | 0% | 0.003016% | 0.000359% | 0.00359% | 0.1002
e) | Electrical works | Solar PV Systems |  | 3.092% | 1% | 5% | 18% | 66% | 10% | 0.03092% | 0.1546% | 0.5566% | 2.041% | 0.3092% | 0.002623% | 0.01311% | 0.04721% | 0.1731% | 0.02623% | 0.2623% | 7.3204
f) | Lift, Escalators & travellators | VHT |  | 2.025% | 1% | 2% | 90% | 2% | 5% | 0.02025% | 0.04049% | 1.822% | 0.04049% | 0.1012% | 0.001717% | 0.003435% | 0.1546% | 0.003435% | 0.008587% | 0.1717% | 4.7934
g) | HVAC works | Chiller, AHU, V Fans, TFA |  | 4.613% | 1% | 5% | 18% | 66% | 10% | 0.04613% | 0.2306% | 0.8303% | 3.044% | 0.4613% | 0.003913% | 0.01956% | 0.07043% | 0.2582% | 0.03913% | 0.3913% | 10.9201
h) | Firefighting works | = |  | 2.774% | 1% | 5% |  | 84% | 10% | 0.02774% | 0.1387% | 0% | 2.33% | 0.2774% | 0.002353% | 0.01177% | 0% | 0.1977% | 0.02353% | 0.2353% | 6.5677
i) | ICT & AV system | = |  | 1.021% | 1% | 5% |  | 84% | 10% | 0.01021% | 0.05106% | 0% | 0.8578% | 0.1021% | 0.0008662% | 0.004331% | 0% | 0.07276% | 0.008662% | 0.08662% | 2.4176
j) | Lighting | = |  | 1.304% | 1% | 2% |  | 92% | 5% | 0.01304% | 0.02607% | 0% | 1.199% | 0.06518% | 0.001106% | 0.002212% | 0% | 0.1017% | 0.005529% | 0.1106% | 3.0863
K) | Misc. works | = |  | 0% | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0
| SUB TOTAL 4 | = |  | 100%
5) | Convention Centre |  | 23.47% | [17 empty] | 654.9368
a) | Civil works including structural steel | Str. Steel, Roofing |  | 32.04% | 1% | 2% | 10% | 84% | 3% | 0.3204% | 0.6408% | 3.204% | 26.91% | 0.9612% | 0.07519% | 0.1504% | 0.7519% | 6.316% | 0.2256% | 7.519% | 209.8451
b) | Internal Finishing including Acoustics and Special Finishes | = |  | 27.42% | 1% | 2% |  | 94% | 3% | 0.2742% | 0.5483% | 0% | 25.77% | 0.8225% | 0.06434% | 0.1287% | 0% | 6.048% | 0.193% | 6.434% | 179.5618
c) | External Finishes including Façade, Special Finishes | = |  | 6.227% | 1% | 2% |  | 95% | 2% | 0.06227% | 0.1245% | 0% | 5.915% | 0.1245% | 0.01461% | 0.02922% | 0% | 1.388% | 0.02922% | 1.461% | 40.7803
d) | Plumbing works | = |  | 1.142% | 1% | 5% |  | 84% | 10% | 0.01142% | 0.05711% | 0% | 0.9595% | 0.1142% | 0.00268% | 0.0134% | 0% | 0.2252% | 0.0268% | 0.268% | 7.4809
e) | Electrical works | Solar PV Systems |  | 2.501% | 1% | 5% |  | 84% | 10% | 0.02501% | 0.1251% | 0% | 2.101% | 0.2501% | 0.005869% | 0.02935% | 0% | 0.493% | 0.05869% | 0.5869% | 16.3809
f) | Lift, Escalators & travellators | VHT |  | 2.813% | 1% | 2% | 90% | 2% | 5% | 0.02813% | 0.05625% | 2.531% | 0.05625% | 0.1406% | 0.0066% | 0.0132% | 0.594% | 0.0132% | 0.033% | 0.66% | 18.4214
g) | HVAC works | Chiller, AHU, V Fans, TFA |  | 3.445% | 1% | 5% | 18% | 66% | 10% | 0.03445% | 0.1723% | 0.6202% | 2.274% | 0.3445% | 0.008085% | 0.04043% | 0.1455% | 0.5336% | 0.08085% | 0.8085% | 22.5655
h) | Firefighting works | = |  | 1.36% | 1% | 5% |  | 84% | 10% | 0.0136% | 0.06799% | 0% | 1.142% | 0.136% | 0.003191% | 0.01595% | 0% | 0.268% | 0.03191% | 0.3191% | 8.9055
i) | ICT & AV system | = |  | 18.26% | 1% | 5% |  | 84% | 10% | 0.1826% | 0.9128% | 0% | 15.33% | 1.826% | 0.04284% | 0.2142% | 0% | 3.598% | 0.4284% | 4.284% | 119.5615
j) | Lighting | = |  | 4.8% | 1% | 2% |  | 92% | 5% | 0.048% | 0.09599% | 0% | 4.416% | 0.24% | 0.01126% | 0.02253% | 0% | 1.036% | 0.05631% | 1.126% | 31.4339
k) | Misc. works | = |  | 0% | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0
| SUB TOTAL 5 | = |  | 100%
6) | Exhibition hall -3 ( basement ) |  | 4.068% | [17 empty] | 113.5269
a) | Civil works including structural steel | = |  | 76% | 1% | 2% |  | 94% | 3% | 0.76% | 1.52% | 0% | 71.44% | 2.28% | 0.03092% | 0.06183% | 0% | 2.906% | 0.09275% | 3.092% | 86.2839
b) | Internal Finishing including Acoustics and Special Finishes | = |  | 9.242% | 1% | 2% |  | 94% | 3% | 0.09242% | 0.1848% | 0% | 8.687% | 0.2773% | 0.003759% | 0.007518% | 0% | 0.3534% | 0.01128% | 0.3759% | 10.4919
c) | External Finishes including Façade, Special Finishes | = |  | 0.04243% | 1% | 2% |  | 95% | 2% | 0.0004243% | 0.0008486% | 0% | 0.04031% | 0.0008486% | 1.726e-05% | 3.452e-05% | 0% | 0.00164% | 3.452e-05% | 0.001726% | 0.048168
d) | Plumbing works | = |  | 1.32% | 1% | 5% |  | 84% | 10% | 0.0132% | 0.06599% | 0% | 1.109% | 0.132% | 0.0005368% | 0.002684% | 0% | 0.04509% | 0.005368% | 0.05368% | 1.4983
e) | Electrical works | Solar PV Systems |  | 3.03% | 1% | 5% | 18% | 66% | 10% | 0.0303% | 0.1515% | 0.5455% | 2% | 0.303% | 0.001233% | 0.006163% | 0.02219% | 0.08135% | 0.01233% | 0.1233% | 3.4403
f) | Lift, Escalators & travellators | VHT |  | 0% | 1% | 2% | 90% | 2% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0
g) | HVAC works | Chiller, AHU, V Fans, TFA |  | 3.697% | 1% | 5% | 18% | 66% | 10% | 0.03697% | 0.1848% | 0.6654% | 2.44% | 0.3697% | 0.001504% | 0.007518% | 0.02707% | 0.09924% | 0.01504% | 0.1504% | 4.1967
h) | Firefighting works | = |  | 4.426% | 1% | 5% |  | 84% | 10% | 0.04426% | 0.2213% | 0% | 3.718% | 0.4426% | 0.0018% | 0.009001% | 0% | 0.1512% | 0.018% | 0.18% | 5.0246
i) | ICT & AV system | = |  | 1.479% | 1% | 5% |  | 84% | 10% | 0.01479% | 0.07396% | 0% | 1.243% | 0.1479% | 0.0006017% | 0.003008% | 0% | 0.05054% | 0.006017% | 0.06017% | 1.6793
j) | Lighting | = |  | 0.7608% | 1% | 2% |  | 92% | 5% | 0.007608% | 0.01522% | 0% | 0.6999% | 0.03804% | 0.0003095% | 0.0006189% | 0% | 0.02847% | 0.001547% | 0.03095% | 0.86373
k) | Misc. works | = |  | 0% | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0
| SUB TOTAL 6 | = |  | 100%
7) | Basement adjacent to Convention Centre |  | 2.143% | [17 empty] | 59.804
a) | Civil works including structural steel | = |  | 68% | 1% | 2% |  | 94% | 3% | 0.68% | 1.36% | 0% | 63.92% | 2.04% | 0.01457% | 0.02914% | 0% | 1.37% | 0.04371% | 1.457% | 40.6662
b) | Internal Finishing including Acoustics and Special Finishes | = |  | 4.667% | 1% | 2% |  | 94% | 3% | 0.04667% | 0.09334% | 0% | 4.387% | 0.14% | 0.001% | 0.002% | 0% | 0.09401% | 0.003% | 0.1% | 2.7912
c) | External Finishes including Façade, Special Finishes | = |  | 0% | 1% | 2% |  | 95% | 2% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0
d) | Plumbing works | = |  | 0.4461% | 1% | 5% |  | 84% | 10% | 0.004461% | 0.02231% | 0% | 0.3747% | 0.04461% | 9.559e-05% | 0.0004779% | 0% | 0.008029% | 0.0009559% | 0.009559% | 0.26679
e) | Electrical works | = |  | 8.33% | 1% | 5% |  | 84% | 10% | 0.0833% | 0.4165% | 0% | 6.997% | 0.833% | 0.001785% | 0.008924% | 0% | 0.1499% | 0.01785% | 0.1785% | 4.9814
f) | Lift, Escalators & travellators | VHT |  | 0% | 1% | 2% | 90% | 2% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0
g) | HVAC works | Chiller, AHU, V Fans, TFA |  | 9.956% | 1% | 5% | 18% | 66% | 10% | 0.09956% | 0.4978% | 1.792% | 6.571% | 0.9956% | 0.002133% | 0.01067% | 0.0384% | 0.1408% | 0.02133% | 0.2133% | 5.9542
h) | Firefighting works | = |  | 5.9% | 1% | 5% |  | 84% | 10% | 0.059% | 0.295% | 0% | 4.956% | 0.59% | 0.001264% | 0.006322% | 0% | 0.1062% | 0.01264% | 0.1264% | 3.5287
i) | Pneumatic Solid waste Plant | = |  | 0% | 1% | 5% |  | 84% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0
j) | ICT & AV system | = |  | 1.763% | 1% | 5% |  | 84% | 10% | 0.01763% | 0.08815% | 0% | 1.481% | 0.1763% | 0.0003778% | 0.001889% | 0% | 0.03173% | 0.003778% | 0.03778% | 1.0543
k) | Lighting | = |  | 0.9385% | 1% | 2% |  | 92% | 5% | 0.009385% | 0.01877% | 0% | 0.8635% | 0.04693% | 0.0002011% | 0.0004022% | 0% | 0.0185% | 0.001006% | 0.02011% | 0.56129
l) | Misc. works | = |  | 0% | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0
| SUB TOTAL 7 | = |  | 100%
8) | Electrical Substation |  | 0.6292% | [17 empty] | 17.5604
a) | Civil works including structural steel | = |  | 36.47% | 1% | 2% |  | 94% | 3% | 0.3647% | 0.7294% | 0% | 34.28% | 1.094% | 0.002295% | 0.004589% | 0% | 0.2157% | 0.006884% | 0.2295% | 6.4045
b) | Internal Finishing including Acoustics and Special Finishes | = |  | 21.62% | 1% | 2% |  | 94% | 3% | 0.2162% | 0.4323% | 0% | 20.32% | 0.6485% | 0.00136% | 0.00272% | 0% | 0.1279% | 0.00408% | 0.136% | 3.7961
c) | External Finishes including Façade, Special Finishes | = |  | 0% | 1% | 2% |  | 95% | 2% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0
d) | Plumbing works | = |  | 0.2916% | 1% | 5% |  | 84% | 10% | 0.002916% | 0.01458% | 0% | 0.245% | 0.02916% | 1.835e-05% | 9.174e-05% | 0% | 0.001541% | 0.0001835% | 0.001835% | 0.05121
e) | Electrical works | = |  | 7.697% | 1% | 5% |  | 84% | 10% | 0.07697% | 0.3848% | 0% | 6.465% | 0.7697% | 0.0004843% | 0.002421% | 0% | 0.04068% | 0.004843% | 0.04843% | 1.3516
f) | Lift, Escalators & travellators | VHT |  | 0% | 1% | 2% | 90% | 2% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0
g) | HVAC works | Chiller, AHU, V Fans, TFA |  | 1.332% | 1% | 5% | 18% | 66% | 10% | 0.01332% | 0.06658% | 0.2397% | 0.8789% | 0.1332% | 8.379e-05% | 0.0004189% | 0.001508% | 0.00553% | 0.0008379% | 0.008379% | 0.23385
h) | Firefighting works | = |  | 2.4% | 1% | 5% |  | 84% | 10% | 0.024% | 0.12% | 0% | 2.016% | 0.24% | 0.000151% | 0.0007549% | 0% | 0.01268% | 0.00151% | 0.0151% | 0.4214
i) | ICT & AV system | = |  | 1.529% | 1% | 5% |  | 84% | 10% | 0.01529% | 0.07644% | 0% | 1.284% | 0.1529% | 9.619e-05% | 0.000481% | 0% | 0.00808% | 0.0009619% | 0.009619% | 0.26847
j) | Lighting | = |  | 0.8408% | 1% | 2% |  | 92% | 5% | 0.008408% | 0.01682% | 0% | 0.7735% | 0.04204% | 5.29e-05% | 0.0001058% | 0% | 0.004867% | 0.0002645% | 0.00529% | 0.14764
k) | Transformers | Transformer |  | 27.82% | 1% | 5% | 85% | 4% | 5% | 0.2782% | 1.391% | 23.65% | 1.113% | 1.391% | 0.00175% | 0.008752% | 0.1488% | 0.007002% | 0.008752% | 0.175% | 4.8856
l) | Misc. works | = |  | 0% | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0
| SUB TOTAL 8 | = |  | 100%
9) | DG Building |  | 2.514% | [17 empty] | 70.1606
a) | Civil works including structural steel | = |  | 29.69% | 1% | 2% |  | 94% | 3% | 0.2969% | 0.5939% | 0% | 27.91% | 0.8908% | 0.007465% | 0.01493% | 0% | 0.7017% | 0.02239% | 0.7465% | 20.834
b) | Internal Finishing including Acoustics and Special Finishes | = |  | 6.482% | 1% | 2% |  | 94% | 3% | 0.06482% | 0.1296% | 0% | 6.093% | 0.1945% | 0.00163% | 0.003259% | 0% | 0.1532% | 0.004889% | 0.163% | 4.548
c) | External Finishes including Façade, Special Finishes | = |  | 2.6% | 1% | 2% |  | 95% | 2% | 0.026% | 0.052% | 0% | 2.47% | 0.052% | 0.0006537% | 0.001307% | 0% | 0.0621% | 0.001307% | 0.06537% | 1.8243
d) | Plumbing works | = |  | 0.1846% | 1% | 5% |  | 84% | 10% | 0.001846% | 0.00923% | 0% | 0.1551% | 0.01846% | 4.641e-05% | 0.000232% | 0% | 0.003898% | 0.0004641% | 0.004641% | 0.12952
e) | Electrical works | = |  | 8.27% | 1% | 5% |  | 84% | 10% | 0.0827% | 0.4135% | 0% | 6.947% | 0.827% | 0.002079% | 0.01039% | 0% | 0.1746% | 0.02079% | 0.2079% | 5.8023
f) | Lift, Escalators & travellators | VHT |  | 0% | 1% | 2% | 90% | 2% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0
g) | HVAC works | Chiller, AHU, V Fans, TFA |  | 5.265% | 1% | 5% | 18% | 66% | 10% | 0.05265% | 0.2632% | 0.9476% | 3.475% | 0.5265% | 0.001323% | 0.006617% | 0.02382% | 0.08735% | 0.01323% | 0.1323% | 3.6937
h) | Firefighting works | = |  | 0.5293% | 1% | 5% |  | 84% | 10% | 0.005293% | 0.02646% | 0% | 0.4446% | 0.05293% | 0.0001331% | 0.0006653% | 0% | 0.01118% | 0.001331% | 0.01331% | 0.37134
i) | ICT & AV system | = |  | 0% | 1% | 5% |  | 84% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0
j) | Lighting | = |  | 0.4249% | 1% | 2% |  | 92% | 5% | 0.004249% | 0.008497% | 0% | 0.3909% | 0.02124% | 0.0001068% | 0.0002136% | 0% | 0.009826% | 0.000534% | 0.01068% | 0.29809
k) | Diesel Generators | Gnrtr, Gas Ins. Swtch. Gr. |  | 44.38% | 1% | 5% | 85% | 4% | 5% | 0.4438% | 2.219% | 37.72% | 1.775% | 2.219% | 0.01116% | 0.05578% | 0.9483% | 0.04463% | 0.05578% | 1.116% | 31.1383
l) | Cooling Towers | Cooling Tower |  | 2.168% | 1% | 5% | 85% | 4% | 5% | 0.02168% | 0.1084% | 1.843% | 0.08672% | 0.1084% | 0.000545% | 0.002725% | 0.04632% | 0.00218% | 0.002725% | 0.0545% | 1.521
m) | Misc. works | = |  | 0% | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0
| SUB TOTAL 9 | = |  | 100%
10) | Fire Station & Disaster Management Building including Medical Centre |  | 0.1225% | [17 empty] | 3.4181
a) | Civil works including structural steel | = |  | 40.91% | 1% | 2% |  | 94% | 3% | 0.4091% | 0.8182% | 0% | 38.46% | 1.227% | 0.000501% | 0.001002% | 0% | 0.0471% | 0.001503% | 0.0501% | 1.3984
b) | Internal Finishing including Acoustics and Special Finishes | = |  | 28.38% | 1% | 2% |  | 94% | 3% | 0.2838% | 0.5677% | 0% | 26.68% | 0.8515% | 0.0003476% | 0.0006952% | 0% | 0.03268% | 0.001043% | 0.03476% | 0.97021
c) | External Finishes including Façade, Special Finishes | = |  | 0% | 1% | 2% |  | 95% | 2% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0
d) | Plumbing works | = |  | 2.117% | 1% | 5% |  | 84% | 10% | 0.02117% | 0.1058% | 0% | 1.778% | 0.2117% | 2.592e-05% | 0.0001296% | 0% | 0.002178% | 0.0002592% | 0.002592% | 0.072351
e) | Electrical works | = |  | 12.62% | 1% | 5% |  | 84% | 10% | 0.1262% | 0.6308% | 0% | 10.6% | 1.262% | 0.0001545% | 0.0007726% | 0% | 0.01298% | 0.001545% | 0.01545% | 0.43127
f) | Lift, Escalators & travellators | VHT |  | 0% | 1% | 2% | 90% | 2% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0
g) | HVAC works | Chiller, AHU, V Fans, TFA |  | 0% | 1% | 5% | 18% | 66% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0
h) | Firefighting works | = |  | 2.211% | 1% | 5% |  | 84% | 10% | 0.02211% | 0.1106% | 0% | 1.857% | 0.2211% | 2.708e-05% | 0.0001354% | 0% | 0.002275% | 0.0002708% | 0.002708% | 0.075579
i) | ICT & AV system | = |  | 0% | 1% | 5% |  | 84% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0
j) | Lighting | = |  | 13.76% | 1% | 2% |  | 92% | 5% | 0.1376% | 0.2752% | 0% | 12.66% | 0.688% | 0.0001685% | 0.000337% | 0% | 0.0155% | 0.0008426% | 0.01685% | 0.47031
k) | Misc. works | = |  | 0% | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0
| SUB TOTAL 10 | = |  | 100%
11) | Plant Room & Service Gallery |  | 1.256% | [17 empty] | 35.0413
a) | Civil works including structural steel | = |  | 0% | 1% | 2% |  | 94% | 3% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0
b) | Internal Finishing including Acoustics and Special Finishes | = |  | 9.124% | 1% | 2% |  | 94% | 3% | 0.09124% | 0.1825% | 0% | 8.577% | 0.2737% | 0.001146% | 0.002291% | 0% | 0.1077% | 0.003437% | 0.1146% | 3.1972
c) | External Finishes including Façade, Special Finishes | = |  | 0% | 1% | 2% |  | 95% | 2% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0
d) | Plumbing works | = |  | 0.2563% | 1% | 5% |  | 84% | 10% | 0.002563% | 0.01282% | 0% | 0.2153% | 0.02563% | 3.218e-05% | 0.0001609% | 0% | 0.002703% | 0.0003218% | 0.003218% | 0.089814
e) | Electrical works | = |  | 7.759% | 1% | 5% |  | 84% | 10% | 0.07759% | 0.388% | 0% | 6.518% | 0.7759% | 0.0009742% | 0.004871% | 0% | 0.08183% | 0.009742% | 0.09742% | 2.7189
f) | Lift, Escalators & travellators | VHT |  | 0% | 1% | 2% | 90% | 2% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0
g) | HVAC works | Chiller, AHU, V Fans, TFA |  | 72.88% | 1% | 5% | 18% | 66% | 10% | 0.7288% | 3.644% | 13.12% | 48.1% | 7.288% | 0.00915% | 0.04575% | 0.1647% | 0.6039% | 0.0915% | 0.915% | 25.539
h) | Firefighting works | = |  | 7.2% | 1% | 5% |  | 84% | 10% | 0.072% | 0.36% | 0% | 6.048% | 0.72% | 0.000904% | 0.00452% | 0% | 0.07594% | 0.00904% | 0.0904% | 2.5231
i) | ICT & AV system | = |  | 1.837% | 1% | 5% |  | 84% | 10% | 0.01837% | 0.09183% | 0% | 1.543% | 0.1837% | 0.0002306% | 0.001153% | 0% | 0.01937% | 0.002306% | 0.02306% | 0.6436
j) | Lighting | = |  | 0.941% | 1% | 2% |  | 92% | 5% | 0.00941% | 0.01882% | 0% | 0.8657% | 0.04705% | 0.0001181% | 0.0002363% | 0% | 0.01087% | 0.0005907% | 0.01181% | 0.32974
k) | Misc. works | = |  | 0% | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0
| SUB TOTAL 11 | = |  | 100%
| GRAND TOTAL(A) | =
PART-B: COST OF INFRASTRUCTURE (Fully facilitated as per Scope, Design Basis
1) | Service Gallery |  | 14.27% | [17 empty] | 398.16
a) | Civil works including structural steel | = |  | 21.7% | 1% | 2% |  | 94% | 3% | 0.217% | 0.4341% | 0% | 20.4% | 0.6511% | 0.03096% | 0.06193% | 0% | 2.911% | 0.09289% | 3.096% | 86.4183
b) | Finishes | = |  | 0% | 1% | 2% |  | 94% | 3% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0
c) | Plumbing works | = |  | 1.122% | 1% | 5% |  | 84% | 10% | 0.01122% | 0.05608% | 0% | 0.9422% | 0.1122% | 0.0016% | 0.008001% | 0% | 0.1344% | 0.016% | 0.16% | 4.4661
d) | HSD Distribution line | = |  | 0% | 1% | 5% |  | 84% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0
e) | PNG line | = |  | 0% | 1% | 5% |  | 84% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0
f) | Electrical works | = |  | 0.3551% | 1% | 5% |  | 84% | 10% | 0.003551% | 0.01776% | 0% | 0.2983% | 0.03551% | 0.0005066% | 0.002533% | 0% | 0.04255% | 0.005066% | 0.05066% | 1.4139
g) | HVAC works | Chiller, AHU, V Fans, TFA |  | 0.2187% | 1% | 5% |  | 84% | 10% | 0.002187% | 0.01093% | 0% | 0.1837% | 0.02187% | 0.000312% | 0.00156% | 0% | 0.02621% | 0.00312% | 0.0312% | 0.87071
h) | Firefighting works | = |  | 0.5681% | 1% | 5% |  | 84% | 10% | 0.005681% | 0.02841% | 0% | 0.4772% | 0.05681% | 0.0008105% | 0.004052% | 0% | 0.06808% | 0.008105% | 0.08105% | 2.2621
i) | Solid Waste pipe Network | = |  | 0.3869% | 1% | 5% |  | 84% | 10% | 0.003869% | 0.01935% | 0% | 0.325% | 0.03869% | 0.0005519% | 0.00276% | 0% | 0.04636% | 0.005519% | 0.05519% | 1.5405
j) | ICT & AV system | = |  | 0.4401% | 1% | 5% |  | 84% | 10% | 0.004401% | 0.022% | 0% | 0.3697% | 0.04401% | 0.0006278% | 0.003139% | 0% | 0.05274% | 0.006278% | 0.06278% | 1.7522
k) | Lighting | = |  | 0% | 1% | 2% |  | 92% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0
l) | Misc. works | = |  | 0% | 1% | 5% |  | 84% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0
2) | Central Control & Command Centre | = |  | 0% | 1% | 5% |  | 84% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0
3) | Electrical Equipment (High Side) including Cabling upto the buildings | HT Panels |  | 6.794% | 1% | 5% |  | 84% | 10% | 0.06794% | 0.3397% | 0% | 5.707% | 0.6794% | 0.009692% | 0.04846% | 0% | 0.8141% | 0.09692% | 0.9692% | 27.0493
4) | HVAC Equipments (High Side) including chilled Water, hot Water and condenser Piping upto the buildings | = |  | 5.359% | 1% | 5% |  | 84% | 10% | 0.05359% | 0.2679% | 0% | 4.501% | 0.5359% | 0.007645% | 0.03822% | 0% | 0.6422% | 0.07645% | 0.7645% | 21.3364
5) | External Plumbing and Mechanical Equipment including Piping upto the buildings and within complex | = |  | 0.1262% | 1% | 5% |  | 84% | 10% | 0.001262% | 0.006312% | 0% | 0.106% | 0.01262% | 0.0001801% | 0.0009005% | 0% | 0.01513% | 0.001801% | 0.01801% | 0.50266
6) | External Fire-fighting and Mechanical Equipment including Piping upto the buildings and within complex and Yard Hydrants for the whole complex | = |  | 0% | 1% | 5% |  | 84% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0
7) | External Sewage System upto the STP | = |  | 0.9925% | 1% | 5% |  | 84% | 10% | 0.009925% | 0.04962% | 0% | 0.8337% | 0.09925% | 0.001416% | 0.007079% | 0% | 0.1189% | 0.01416% | 0.1416% | 3.9516
8) | External Storm Water drainage including Rain Water Harvesting System | = |  | 3.997% | 1% | 5% |  | 84% | 10% | 0.03997% | 0.1999% | 0% | 3.358% | 0.3997% | 0.005702% | 0.02851% | 0% | 0.479% | 0.05702% | 0.5702% | 15.9154
9) | Pneumatic Solid Waste Management system including inlets and piping, | = |  | 2.976% | 1% | 5% |  | 84% | 10% | 0.02976% | 0.1488% | 0% | 2.5% | 0.2976% | 0.004246% | 0.02123% | 0% | 0.3567% | 0.04246% | 0.4246% | 11.851
10) | Solid Waste Plant and Compost Plant including Transport Vehicles, | Solid Pneumatic Waste |  | 1.028% | 1% | 5% | 80% | 4% | 10% | 0.01028% | 0.0514% | 0.8224% | 0.04112% | 0.1028% | 0.001467% | 0.007333% | 0.1173% | 0.005866% | 0.01467% | 0.1467% | 4.0931
11) | STP and Pumps | STP |  | 1.908% | 1% | 5% | 80% | 4% | 10% | 0.01908% | 0.09538% | 1.526% | 0.0763% | 0.1908% | 0.002721% | 0.01361% | 0.2177% | 0.01089% | 0.02721% | 0.2721% | 7.5953
12) | WTP and Pumps | WTP |  | 0.09531% | 1% | 5% | 80% | 4% | 10% | 0.0009531% | 0.004765% | 0.07624% | 0.003812% | 0.009531% | 0.000136% | 0.0006798% | 0.01088% | 0.0005438% | 0.00136% | 0.0136% | 0.37947
13) | Landscaping |  |  | 0% | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0
a) | Softscape & Hard scape, Horticulture | = |  | 13.39% | 1% | 2% |  | 95% | 2% | 0.1339% | 0.2678% | 0% | 12.72% | 0.2678% | 0.0191% | 0.0382% | 0% | 1.815% | 0.0382% | 1.91% | 53.3133
b) | Irrigation & drainage | = |  | 0.8545% | 1% | 2% |  | 95% | 2% | 0.008545% | 0.01709% | 0% | 0.8118% | 0.01709% | 0.001219% | 0.002438% | 0% | 0.1158% | 0.002438% | 0.1219% | 3.4024
c) | water bodies, Fountain | = |  | 3.797% | 1% | 2% |  | 95% | 2% | 0.03797% | 0.07595% | 0% | 3.608% | 0.07595% | 0.005417% | 0.01083% | 0% | 0.5147% | 0.01083% | 0.5417% | 15.1201
d) | Plazas, Pergolas & Canopies | = |  | 0.9711% | 1% | 2% |  | 95% | 2% | 0.009711% | 0.01942% | 0% | 0.9226% | 0.01942% | 0.001385% | 0.002771% | 0% | 0.1316% | 0.002771% | 0.1385% | 3.8667
e) | Street Furniture | = |  | 0.9763% | 1% | 2% |  | 95% | 2% | 0.009763% | 0.01953% | 0% | 0.9275% | 0.01953% | 0.001393% | 0.002786% | 0% | 0.1323% | 0.002786% | 0.1393% | 3.8874
14) | Pathways & Walkway | = |  | 3.22% | 1% | 2% |  | 95% | 2% | 0.0322% | 0.0644% | 0% | 3.059% | 0.0644% | 0.004594% | 0.009187% | 0% | 0.4364% | 0.009187% | 0.4594% | 12.8206
15) | Open Exhibition Area | = |  | 0% | 1% | 2% |  | 95% | 2% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0
16) | Roads, Ramps, Tunnels | = |  | 24.48% | 1% | 2% |  | 95% | 2% | 0.2448% | 0.4896% | 0% | 23.25% | 0.4896% | 0.03492% | 0.06984% | 0% | 3.317% | 0.06984% | 3.492% | 97.4606
17) | External area Lighting | = |  | 4.242% | 1% | 2% |  | 95% | 2% | 0.04242% | 0.08485% | 0% | 4.03% | 0.08485% | 0.006052% | 0.0121% | 0% | 0.5749% | 0.0121% | 0.6052% | 16.8912
| GRAND TOTAL(B) | = |  | 100%
PART-C: COST OF SPECIALISED WORKS (Fully facilitated as per Scope, Design Basis | [20 empty] | 341.9916
Report, Technical Specifications, Design Intent, Tender Drawings & Tender Documents in complete)
12.25%
1) | Retractable seating (Automatic) | [19 empty] | 0
a) | Convention Centre | Retractible, Fixed Seating |  | 43.96% | 1% | 5% | 80% | 4% | 10% | 0.4396% | 2.198% | 35.17% | 1.759% | 4.396% | 0.05387% | 0.2694% | 4.31% | 0.2155% | 0.5387% | 5.387% | 150.3515
b) | Exhibition Hall | Retractible, Fixed Seating |  | 6.326% | 1% | 5% | 80% | 4% | 10% | 0.06326% | 0.3163% | 5.061% | 0.2531% | 0.6326% | 0.007752% | 0.03876% | 0.6202% | 0.03101% | 0.07752% | 0.7752% | 21.636
2) | LED on External Facade | LED |  | 40.93% | 1% | 5% | 80% | 4% | 10% | 0.4093% | 2.046% | 32.74% | 1.637% | 4.093% | 0.05015% | 0.2507% | 4.012% | 0.2006% | 0.5015% | 5.015% | 139.968
3) | Sliding folding / Vertical Partitions (Automatic) | = |  | 0% | [5 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0
a) | Sliding/Folding Acoustic Partitions. | Sliding/Folding - Ver. Prtn. |  | 1.583% | 1% | 5% | 80% | 4% | 10% | 0.01583% | 0.07916% | 1.267% | 0.06333% | 0.1583% | 0.00194% | 0.0097% | 0.1552% | 0.00776% | 0.0194% | 0.194% | 5.4144
b) | Vertically Retractable Non Acoustic, Partitions | Sliding/Folding - Ver. Prtn. |  | 5.835% | 1% | 5% | 80% | 4% | 10% | 0.05835% | 0.2918% | 4.668% | 0.2334% | 0.5835% | 0.00715% | 0.03575% | 0.572% | 0.0286% | 0.0715% | 0.715% | 19.9561
4) | Internal / External Signage | = |  | 1.364% | 1% | 5% |  | 89% | 5% | 0.01364% | 0.06821% | 0% | 1.214% | 0.06821% | 0.001672% | 0.008358% | 0% | 0.1488% | 0.008358% | 0.1672% | 4.6656
| GRAND TOTAL(C ) | = |  | 100%
|  |  | 100% | [9 empty] | Check |  | 1% | 2.986% | 15.97% | 75.07% | 4.971% | 100% | 2791
Project Fixed Preliminaries

## LL
ACTUAL
LONG LEAD ITEMS | ITEM NO | PROCUREMENT ITEM CONSIDERED | PERCENTAGE | COST OF PRICE BID ITEM | PROCUREMENT COST | ACTUAL | PROCUREMENT | PERCENTAGE | PRICE BID | PROCUREMENT COST
PART-A: COST OF BUILDING WORKS (Fully facilitated as per Scope, Design Basis
Exhibition Hall No. 1
Civil works including structural steel, roofing complete | 1 a | Structural steel, roofing | 10% | 145.9615 | 14.5962 |  |  | 21% | 145.9615 | 30.6519
Electrical works | 1 e | Solar PV system,Transformer, HT Cables | 18% | 13.3856 | 2.4094 | 10.373 | 7.7797 | 38.41% | 13.3856 | 5.1409
Lift, Escalators & travellators | 1 f | VHT | 90% | 3.1926 | 2.8734 | 7.4 | 5.55 | 85.78% | 3.1926 | 2.7386
HVAC works | 1 g | AHU,V fans, TFA, PHE, CHW Pipes Etc | 18% | 11.519 | 2.0734 | 8.43 | 6.3225 | 40% | 11.519 | 4.6076
Exhibition Hall No. 2
Civil works including structural steel | 2 a | Str. Steel, Roofing | 10% | 138.2892 | 13.8289 |  |  | 21% | 138.2892 | 29.0407
Electrical works | 2 e | Solar PV system,Transformer, HT Cables | 18% | 12.4811 | 2.2466 | 8.83 | 6.6225 | 33.44% | 12.4811 | 4.1742
Lift, Escalators & travellators | 2 f | VHT | 90% | 4.3091 | 3.8782 | 9.78 | 7.824 | 85.95% | 4.3091 | 3.7039
HVAC works | 2 g | AHU,V fans, TFA, PHE, CHW Pipes Etc | 18% | 13.2824 | 2.3908 | 7.5 | 5.625 | 31% | 13.2824 | 4.1175
FOYER 1
Civil works including structural steel | 3 a | Str. Steel, Roofing | 10% | 138.6846 | 13.8685 |  |  | 21% | 138.6846 | 29.1238
Electrical works | 3 e | Solar PV system,Transformer, HT Cables | 18% | 6.8707 | 1.2367 |  |  | 38.41% | 6.8707 | 2.6388
Lift, Escalators & travellators | 3 f | VHT | 90% | 3.2806 | 2.9526 |  |  | 85.78% | 3.2806 | 2.8141
HVAC works | 3 g | AHU,V fans, TFA, PHE, CHW Pipes Etc | 18% | 9.2864 | 1.6716 |  | 0 | 40% | 9.2864 | 3.7146
FOYER 2
Civil works including structural steel | 4 a | Str. Steel, Roofing | 10% | 133.9662 | 13.3966 |  |  | 21% | 133.9662 | 28.1329
Electrical works | 4 e | Solar PV system,Transformer, HT Cables | 18% | 7.3204 | 1.3177 |  |  | 33.44% | 7.3204 | 2.4483
Lift, Escalators & travellators | 4 f | VHT | 90% | 4.7934 | 4.314 |  |  | 86% | 4.7934 | 4.1223
HVAC works | 4 g | AHU,V fans, TFA, PHE, CHW Pipes Etc | 18% | 10.9201 | 1.9656 |  | 0 | 31% | 10.9201 | 3.3852
CONVENTION CENTER
Civil works including structural steel | 5 a | Str. Steel, Roofing | 10% | 209.8451 | 20.9845 |  |  | 21% | 209.8451 | 44.0675
Electrical works | 5 e | Solar PV system,Transformer, HT Cables | 18% | 16.3809 | 2.9486 | 11.271 | 8.4533 | 51.6% | 16.3809 | 8.4533
Lift, Escalators & travellators | 5 f | VHT | 90% | 18.4214 | 16.5792 | 10.1 | 7.575 | 86% | 18.4214 | 15.8424
HVAC works | 5 g | AHU,V fans, TFA, PHE, CHW Pipes Etc | 18% | 22.5655 | 4.0618 | 10.59 | 7.9425 | 49% | 22.5655 | 11.0571
BASEMENT EXHIBITION 3
Electrical works | 6 e | Transformer | 18% | 3.4403 | 0.61925 | 1.3 | 0.975 | 38% | 3.4403 | 1.3073
HVAC works | 6 g | V fans, Pumps, CHW Pipes Etc | 18% | 4.1967 | 0.75541 | 2.1 |  | 50% | 4.1967 | 2.0984
BASEMENT ADJACENT TO CONEVENTION CENTER
HVAC works | 7 g | V fans, CHW Pipes Etc | 18% | 5.9542 | 1.0718 | 2.75 |  | 46% | 5.9542 | 2.7389
ELECTRICAL SUBSTATION
HVAC works | 8 g | V fans, CHW Pipes Etc | 18% | 0.23385 | 0.042093 | 0.18 |  | 75% | 0.23385 | 0.17539
Transformers | 8 k | Transformer | 85% | 4.8856 | 4.1528 | 4 | 3.66 | 75% | 4.8856 | 3.6642
DG BUILDING
HVAC works | 9 g | V fans, CHW Pipes Etc | 18% | 3.6937 | 0.66487 | 1.5 |  | 40% | 3.6937 | 1.4775
Diesel Generators | 9 k | Generators | 85% | 31.1383 | 26.4676 | 28.8 | 21.6 | 80% | 31.1383 | 24.9106
Cooling Towers | 9 l | Cooling Tower | 85% | 1.521 | 1.2929 | 1 |  | 80% | 1.521 | 1.2168
PLANT ROOM AND SERVICE GALLERY
HVAC works | 11 g | Chillers, ring mains, Heat pumps | 18% | 25.539 | 4.597 | 25.54 | 21.4536 | 75% | 25.539 | 19.1542
PART-B: COST OF INFRASTRUCTURE (Fully facilitated as per Scope, Design Basis
SERVICE GALLERY
HVAC works | 1 g | CHW Pipes | 84% | 0.87071 | 0.73139 | 0.65 |  | 75% | 0.87071 | 0.65303
ELECTRICAL EQUIPMENTS | 3 | HT Panels, Grid sub stations | 84% | 27.0493 | 22.7214 | 24 |  | 75% | 27.0493 | 20.287
SOLID WASTE PLANT | 10 | Solid Pneumatic Waste | 80% | 4.0931 | 3.2745 | 35 | 26.25 | 75% | 4.0931 | 3.0698
STP | 11 | STP | 80% | 7.5953 | 6.0762 | 8 |  | 75% | 7.5953 | 5.6965
WTP | 12 | WTP | 80% | 0.37947 | 0.30358 | 0.5 |  | 75% | 0.37947 | 0.2846
PART-C: COST OF SPECIALISED WORKS (Fully facilitated as per Scope, Design Basis | [10 empty] | 0
RETRACTABLE SEATING
Convention Centre | 1 a | Retractible, Fixed Seating | 80% | 150.3515 | 120.2812 | 65.19 |  | 43.36% | 65.19 | 28.2653
Exhibition Hall | 1 b | Retractible, Fixed Seating | 80% | 21.636 | 17.3088 | 60.9 |  | 75% | 21.636 | 16.227
LED ON FAÇADE | 2 | LED | 80% | 139.968 | 111.9744 | 75 |  | 53.58% | 139.968 | 75
SLIDING FOLDING PARTITIONS
Sliding/Folding Acoustic Partitions. | 3 a | Sliding/Folding - Ver. Prtn. | 80% | 5.4144 | 4.3315 | 23 |  | 75% | 5.4144 | 4.0608
Vertically Retractable Non Acoustic, Partitions | 3 b | Sliding/Folding - Ver. Prtn. | 80% | 19.9561 | 15.9649 |  |  | 80% | 19.9561 | 15.9649
|  |  |  | 1382.6726 | 472.2258 | 443.684
CHLLAR PIPES @ 1200 DIAMETER | 30
CABLES | 40
ADDITIONAL COST ON SOLID WASTE MGMT | 30
X RAY MACHINES | 16

## LL 1
S.NO | ITEM DESCRIPTION |  | QUANTITY | UNIT | RATE IN RS | ESTIMATED COST | PAYABLE COST AGAINST PRICE BID ITEMS( AT DELIVERY )
1 | ST STEEL |  | 30000 | MT | 50000 | 150 | 150
2 | ROOFING |  | 102921 | SQM | 4500 | 11.02 | 11.02
ELECTRICAL WORKS
3 | SOLAR PV SYSTEM
a | EH 1 AND FOYER 1 | SOLAR PV SYSTEM | 1532 | Nos | 60000 | 9.19 | 9.1532
b | EH 2 AND FOYER 2 |  | 1275 | Nos | 60000 | 7.65 | 7.5475
c | CONVENTION |  | 1664 | Nos | 60000 | 9.984 | 10.0106
4 | TRANSFORMER
a | EH 1 AND FOYER 1 |  | 9100 | KVA | 1300 | 1.18 | 1.1753
b | EH 2 AND FOYER 2 |  | 9100 | KVA | 1300 | 1.183 | 1.1671
c | CONVENTION |  | 7400 | KVA | 1300 | 1.287 | 1.2904
5 | CABLES HT |  |  |  |  | 39.6
a | EH 1 AND FOYER 1 |  | 50000 | MTS | 1100 | 5.55 | 4.86
b | EH 2 AND FOYER 2 |  | 71455 | MTS | 1100 | 7.86 | 6.14
c | CONVENTION |  | 80455 | MTS | 1100 | 8.85 | 0.99
d | EX 3 |  | 56091 | MTS | 1100 | 6.17 | 1.27
e | BSMT adjacent to CC |  | 24818 | MTS | 1100 | 2.73 | 3.74
f | ELECTRICAL SUBSTATION |  | 9091 | MTS | 1100 | 1 | 1.01
g | DG BUILDING |  | 39545 | MTS | 1100 | 4.3499 | 4.35
h | PLANT ROOM AND GALLERY |  | 18545 | MTS | 1100 | 2.04 | 2.04
i | Service GALLERY |  | 9545 | MTS | 1100 | 1.05 | 1.05
6 | VHT
a | EH 1 AND FOYER 1 |  |  |  |  | 11.73 | 5.57
| Main |  | 10 | Nos | 4500000 | 4.5
| Service |  | 5 | Nos | 5500000 | 2.75
| Escalator |  | 6 | Nos | 5800000 | 3.48
| Ramps |  | 2 | Nos | 5000000 | 1
b | EH 2 AND FOYER 2 |  |  |  |  | 11.2 | 7.8299
| Main |  | 14 | Nos | 4500000 | 6.3
| Service |  | 6 | Nos | 5500000 | 3.3
| Travellator |  | 1 | Nos | 16000000 | 1.6
c | CONVENTION |  |  |  |  | 23.87 | 15.84
| Main |  | 16 | Nos | 4500000 | 7.2
| Service |  | 5 | Nos | 5500000 | 2.75
| Escalator |  | 24 | Nos | 5800000 | 13.92
7 | HVAC
| EH 1 AND FOYER 1 |  |  |  |  | 8.43 | 8.32
a | AHU |  | 21 | Nos | 300000 | 0.63
b | V Fans |  | 20 | Nos | 200000 | 0.4
c | TFA |  | 20 | Nos | 200000 | 0.4
d | PHE |  | 2 | Nos | 5000000 | 1
e | CHW Pipes |  | 1200 | MTS | 50000 | 6
| EH 2 AND FOYER 2 |  |  |  |  | 7.43 | 7.5
a | AHU |  | 21 | Nos | 300000 | 0.63
b | V Fans |  | 20 | Nos | 200000 | 0.4
c | TFA |  | 20 | Nos | 200000 | 0.4
d | PHE |  | 2 | Nos | 5000000 | 1
e | CHW Pipes |  | 1000 | MTS | 50000 | 5
| CONVENTION |  |  |  |  | 11.09 | 11.06
a | AHU |  | 53 | Nos | 300000 | 1.59
b | V Fans |  | 25 | Nos | 200000 | 0.5
c | TFA |  | 25 | Nos | 200000 | 0.5
d | PHE |  | 3 | Nos | 5000000 | 1.5
e | CHW Pipes |  | 1400 | MTS | 50000 | 7
| BSMT 3 |  |  |  |  | 2.1 | 2.1
a | V Fans |  | 25 | Nos | 200000 | 0.5
b | Pumps |  | 5 | Nos | 1000000 | 0.5
c | CHW Pipes |  | 220 | MTS | 50000 | 1.1
| BSMT ADJACENT TO CC |  |  |  |  | 2.6 | 2.74
a | V Fans |  | 30 | Nos | 200000 | 0.6
b | CHW Pipes |  | 400 | MTS | 50000 | 2
| ELECTRICAL SUBSTATION |  |  |  |  | 1.95 | 1.8
a | CHW Pipes |  | 50 | MTS | 50000 | 0.25
| DG BUILDING |  |  |  |  | 1.7 | 1.7
a | V Fans |  | 10 | Nos | 200000 | 0.2
b | CHW Pipes |  | 300 | MTS | 50000 | 1.5
| PLANT ROOM AND GALLERY |  |  |  |  | 19.6 | 19.15
a | Chillar |  | 6 | Nos | 26000000 | 15.6
b | Ring mains |  | 400 | MTS | 50000 | 2
c | Heat pumps |  | 8 | Nos | 2500000 | 2
SERVICE GALLERY
a | Ring mains |  | 160 | MTS | 50000 | 0.8 | 0.65
BSMT E 3
a | Transformer |  | 10000 | KVA | 1300 | 1.3 | 1.31
ELECT SUB STATION
a | Transformer |  | 2 | Nos | 20000000 | 4 | 3.66
DG BUILDING
a | Generator |  | 36000 | KVA | 8000 | 28.8 | 24.91
b | Cooling tower |  | 14400 | TR | 700 | 1.008 | 1.22
| ELECTRICAL EQUIPMENTS |  |  |  |  | 24 | 20.29
a | HT Panel |  |  |  |  | 4
b | Grid sub station |  |  |  |  | 20
| SOLID WASTE |  |  |  |  | 35 | 3.07
| STP |  |  |  |  | 8 | 5.7
| WTP |  |  |  |  | 0.5 | 0.28
RETRACTABLE SEATING
| Convention |  |  |  |  | 65.19 | 64.65
| Exhibition halls |  |  |  |  | 60.9 | 16.23
| LED ON FAÇADE |  | 8800 | SQM | 100000 | 88 | 88.18
| SLIDING FOLDING |  |  |  |  | 23 | 19.03

## PT-LL2
As per EE internal Calculation
Sum of ESTIMATED COST
Building / Zone | Material Description | Total
EH 1 AND FOYER 1 | Structural Steel, Roofing, Reinforcement Steel, Safety Material | 106.0149
| VHT | 11.73
| GRC Cladding & ACM | 9.2352
| GRC False Ceiling | 10.6618
| Solar PV Syst, Transformer | 10.37
| Fire Protection System | 4.5421
| AHU, V Fans, TFA, Plate Heat Exchanger | 3.77 | GRC Cladding & ACM
| PHE Systems | 1.4675 | GRC False Ceiling
Sub Total |  | 157.7916
EH 2 AND FOYER 2 | Structural Steel, Roofing, Reinforcement Steel, Safety Material | 101.3869
| VHT | 11.2
| GRC Cladding & ACM | 13.1021
| GRC False Ceiling | 18.48
| Solar PV Syst, Transformer | 8.833
| Fire Protection System | 3.978
| AHU, V Fans, TFA, Plate Heat Exchanger | 3.77
| PHE Systems | 2.755
Sub Total |  | 163.5049
Exhibition Hall 3 | Reinforcement | 10.3574
| Transformer | 1.3
| Fire Protection System | 2.2606
(blank)
| V Fans, Pumps | 1.125
Sub Total |  | 15.043
Convention Center | Structural Steel, Roofing, Reinforcement Steel, Safety Material | 77.0796
| VHT | 23.87
| GRC Cladding & ACM | 16.3128
| GRC False Ceiling | 8.4324
| Solar PV Syst, Transformer | 11.271
| Fire Protection System | 4.6976
| AHU, V Fans, TFA, Plate Heat Exchanger | 6.835
| PHE Systems | 2.11
Sub Total |  | 150.6085
Basement Convention Center | Reinforcement | 4.8815
| V Fans | 0.75
| Fire Protection System | 1.7771
Sub Total |  | 7.4086
ELECTRICAL SUBSTATION | Reinforcement | 0.76879
| Fire Protection System | 0.16268
Sub Total |  | 0.93147
DG BUILDING | Reinforcement | 2.5009
| V Fans | 0.25
| Fire Protection System | 0.4288
| Generators including Cooling Tower | 29.808
Sub Total |  | 32.9877
Fire Station | Reinforcement | 0.16786
| Fire Protection System | 0.0544
Sub Total |  | 0.22226
Guard Room | Fire Protection System | 0.0034
Sub Total |  | 0.0034
Plant Room And Gallery | (blank) | 0
| Chillar, Heat pumps | 17.6
Sub Total |  | 17.6
SERVICE GALLERY | Reinforcement | 10.3736
| Ring mains | 0.8
| Fire Protection System | 2.5418
(blank)
Sub Total |  | 13.7154
External Development Works | CHW Pipes | 22.85
| STP | 8
| WTP | 0.5
| 66KV HT Panels, HT Cables, 66KV Transformer | 29.5727
| Pneumatic Solid Waste Management System | 35
Sub Total |  | 95.9227
Special Items | Retractible, Fixed Seating - Convention Centre | 65.19
| Retractible, Fixed Seating - Exhibition Hall | 60.9
| LED on External Facade | 88
| Sliding/Folding - Ver. Prtn. | 23
Sub Total |  | 237.09
Grand Total |  | 892.8295

## PT-LL2 (Sub Breakup)-Do Not Chg
As per EE internal Calculation
Sum of ESTIMATED COST |  | Single Material
Building / Zone | Material Description | Reinforcement Steel | Structural Steel Works | Roofing Works | Safety Equipments | AHU | V Fans | Pumps | TFA | Plate Heat Exchanger | Fire Protection System | GRC False Ceiling | GRC Cladding & ACM | Solar PV System | Transformer | VHT | Generators including Cooling Tower | Chillar | Heat pumps | Ring mains | 66KV HT Panel | Cables HT | 66KV Transformer | CHW Pipes | WTP | STP | Retractable Seating | PHE Systems | Pneumatic Solid Waste Management System | LED on External Facade | Sliding/Folding - Ver. Prtn. | Grand Total
EH 1 AND FOYER 1 | Structural Steel, Roofing, Reinforcement Steel, Safety Material | 32.23% | 53.23% | 10.48% | 4.062% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| AHU, V Fans, TFA, Plate Heat Exchanger | 0% | 0% | 0% | 0% | 38.99% | 13.26% | 0% | 21.22% | 26.53% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| Fire Protection System | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| GRC False Ceiling | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| GRC Cladding & ACM | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| PHE Systems | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 100%
| Solar PV Syst, Transformer | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 88.62% | 11.38% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| VHT | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
EH 2 AND FOYER 2 | Structural Steel, Roofing, Reinforcement Steel, Safety Material | 32.23% | 53.23% | 10.48% | 4.049% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| AHU, V Fans, TFA, Plate Heat Exchanger | 0% | 0% | 0% | 0% | 38.99% | 13.26% | 0% | 21.22% | 26.53% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| Fire Protection System | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| GRC False Ceiling | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| GRC Cladding & ACM | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| PHE Systems | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 100%
| Solar PV Syst, Transformer | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 86.61% | 13.39% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| VHT | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
Exhibition Hall 3 | Reinforcement | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| V Fans, Pumps | 0% | 0% | 0% | 0% | 0% | 55.56% | 44.44% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| Fire Protection System | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| Transformer | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
Convention Center | Structural Steel, Roofing, Reinforcement Steel, Safety Material | 32.68% | 53.97% | 10.63% | 2.722% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| AHU, V Fans, TFA, Plate Heat Exchanger | 0% | 0% | 0% | 0% | 54.28% | 9.144% | 0% | 14.63% | 21.95% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| Fire Protection System | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| GRC False Ceiling | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| GRC Cladding & ACM | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| PHE Systems | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 100%
| Solar PV Syst, Transformer | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 88.58% | 11.42% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| VHT | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
Basement Convention Center | Reinforcement | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| V Fans | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| Fire Protection System | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
ELECTRICAL SUBSTATION | Reinforcement | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| Fire Protection System | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
DG BUILDING | Reinforcement | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| V Fans | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| Fire Protection System | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| Generators including Cooling Tower | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
Fire Station | Reinforcement | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| Fire Protection System | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
Guard Room | Fire Protection System | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
Plant Room And Gallery | Chillar, Heat pumps | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 88.64% | 11.36% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
SERVICE GALLERY | Reinforcement | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| Fire Protection System | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| Ring mains | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
External Development Works | 66KV HT Panels, HT Cables, 66KV Transformer | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 13.53% | 72.95% | 13.53% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| CHW Pipes | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| WTP | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| STP | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 100%
| Pneumatic Solid Waste Management System | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 100%
Special Items | Retractible, Fixed Seating - Convention Centre | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 100%
| Retractible, Fixed Seating - Exhibition Hall | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 100%
| LED on External Facade | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 100%
| Sliding/Folding - Ver. Prtn. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100%
Grand Total |  | 13.56% | 17.02% | 3.352% | 1.177% | 0.7448% | 0.364% | 0.056% | 0.2912% | 0.392% | 2.29% | 4.208% | 4.329% | 3.004% | 0.5544% | 5.242% | 3.339% | 1.747% | 0.224% | 0.0896% | 0.448% | 2.416% | 0.448% | 2.559% | 0.056% | 0.896% | 14.12% | 0.7093% | 3.92% | 9.856% | 2.576% | 100%

## VHT New
6 | VHT |  | Old | New | To get from Rajib
a | EH 1 AND FOYER 1 |  |  |  | Eh | Fy
| Passenger Lift | VHT | 10 | 10
| Service Lift | VHT | 5 | 5
| Escalator | VHT | 6 | 4
| Ramps | VHT | 2 | 2
b | EH 2 AND FOYER 2
| Passenger Lift | VHT | 14 | 14
| Service Lift | VHT | 6 | 6
| Escalator | VHT |  | 2
| Travellator | VHT | 1 | 2
c | CONVENTION
| Passenger Lift | VHT | 16 | 17
| Service Lift | VHT | 5 | 5
| Escalator | VHT | 24 | 30
| Mobile Platform | VHT |  | 2
|  |  | 89 | 99

## LL 2
S.NO | ITEM DESCRIPTION | Single Material | Material Description | Discipline of Material | Building / Zone | Price Bid | QUANTITY | UNIT | RATE IN RS | ESTIMATED COST | PAYABLE COST AGAINST PRICE BID ITEMS( AT DELIVERY ) | Percentage of Project Cost
1 | ST STEEL | [5 empty] | 30000 | MT | 50000 | 150 | 150 | 5.3744
2 | ROOFING | [5 empty] | 102921 | SQM | 3150 | 32.42 | 32.42 | 1.1616
ELECTRICAL WORKS
3 | SOLAR PV SYSTEM | [8 empty] | 26.824
a | EH 1 AND FOYER 1 | Solar PV System | Solar PV Syst, Transformer | ELECTRICAL WORKS | EH 1 AND FOYER 1 |  | 1532 | KW | 60000 | 9.19 | 9.1532 | 0.32796
b | EH 2 AND FOYER 2 | Solar PV System | Solar PV Syst, Transformer | ELECTRICAL WORKS | EH 2 AND FOYER 2 |  | 1275 | KW | 60000 | 7.65 | 7.5475 | 0.27042
c | CONVENTION | Solar PV System | Solar PV Syst, Transformer | ELECTRICAL WORKS | Convention Center |  | 1664 | KW | 60000 | 9.984 | 10.0106 | 0.35867
4 | TRANSFORMER | [8 empty] | 3.65
a | EH 1 AND FOYER 1 | Transformer | Solar PV Syst, Transformer | ELECTRICAL WORKS | EH 1 AND FOYER 1 |  | 9100 | KVA | 1300 | 1.18 | 1.1753 | 0.04211
b | EH 2 AND FOYER 2 | Transformer | Solar PV Syst, Transformer | ELECTRICAL WORKS | EH 2 AND FOYER 2 |  | 9100 | KVA | 1300 | 1.183 | 1.1671 | 0.041818
c | CONVENTION | Transformer | Solar PV Syst, Transformer | ELECTRICAL WORKS | Convention Center |  | 7400 | KVA | 1300 | 1.287 | 1.2904 | 0.046235
5 | CABLES HT | [8 empty] | 21.5727
a | EH 1 AND FOYER 1 | Cables HT | 66KV HT Panels, HT Cables, 66KV Transformer |  | External Development Works |  | 50000 | MTS | 600 | 3 | 4.86 | 0.17413
b | EH 2 AND FOYER 2 | Cables HT | 66KV HT Panels, HT Cables, 66KV Transformer |  | External Development Works |  | 71455 | MTS | 600 | 4.2873 | 6.14 | 0.21999
c | CONVENTION | Cables HT | 66KV HT Panels, HT Cables, 66KV Transformer |  | External Development Works |  | 80455 | MTS | 600 | 4.8273 | 0.99 | 0.035471
d | EX 3 | Cables HT | 66KV HT Panels, HT Cables, 66KV Transformer |  | External Development Works |  | 56091 | MTS | 600 | 3.3655 | 1.27 | 0.045503
e | BSMT adjacent to CC | Cables HT | 66KV HT Panels, HT Cables, 66KV Transformer |  | External Development Works |  | 24818 | MTS | 600 | 1.4891 | 3.74 | 0.134
f | ELECTRICAL SUBSTATION | Cables HT | 66KV HT Panels, HT Cables, 66KV Transformer |  | External Development Works |  | 9091 | MTS | 600 | 0.54546 | 1.01 | 0.036188
g | DG BUILDING | Cables HT | 66KV HT Panels, HT Cables, 66KV Transformer |  | External Development Works |  | 39545 | MTS | 600 | 2.3727 | 4.35 | 0.15586
h | PLANT ROOM AND GALLERY | Cables HT | 66KV HT Panels, HT Cables, 66KV Transformer |  | External Development Works |  | 18545 | MTS | 600 | 1.1127 | 2.04 | 0.073092
i | Service GALLERY | Cables HT | 66KV HT Panels, HT Cables, 66KV Transformer |  | External Development Works |  | 9545 | MTS | 600 | 0.5727 | 1.05 | 0.037621
6 | VHT | [8 empty] | 46.8
a | EH 1 AND FOYER 1 | [8 empty] | 11.73 | 5.57 | 0.19957
| Passenger Lift | VHT | VHT |  | EH 1 AND FOYER 1 |  | 10 | Nos | 4500000 | 4.5
| Service Lift | VHT | VHT |  | EH 1 AND FOYER 1 |  | 5 | Nos | 5500000 | 2.75
| Escalator | VHT | VHT |  | EH 1 AND FOYER 1 |  | 6 | Nos | 5800000 | 3.48
| Ramps | VHT | VHT |  | EH 1 AND FOYER 1 |  | 2 | Nos | 5000000 | 1
b | EH 2 AND FOYER 2 | [8 empty] | 11.2 | 7.8299 | 0.28054
| Passenger Lift | VHT | VHT |  | EH 2 AND FOYER 2 |  | 14 | Nos | 4500000 | 6.3
| Service Lift | VHT | VHT |  | EH 2 AND FOYER 2 |  | 6 | Nos | 5500000 | 3.3
| Travellator | VHT | VHT |  | EH 2 AND FOYER 2 |  | 1 | Nos | 16000000 | 1.6
c | CONVENTION | [8 empty] | 23.87 | 15.84 | 0.56754
| Passenger Lift | VHT | VHT |  | Convention Center |  | 16 | Nos | 4500000 | 7.2
| Service Lift | VHT | VHT |  | Convention Center |  | 5 | Nos | 5500000 | 2.75
| Escalator | VHT | VHT |  | Convention Center |  | 24 | Nos | 5800000 | 13.92
7 | HVAC
| EH 1 AND FOYER 1 | [8 empty] | 9.77 | 8.32 | 0.2981
a | AHU | AHU | AHU, V Fans, TFA, Plate Heat Exchanger | HVAC | EH 1 AND FOYER 1 |  | 21 | Nos | 700000 | 1.47
b | V Fans | V Fans | AHU, V Fans, TFA, Plate Heat Exchanger | HVAC | EH 1 AND FOYER 1 |  | 20 | Nos | 250000 | 0.5
c | TFA | TFA | AHU, V Fans, TFA, Plate Heat Exchanger | HVAC | EH 1 AND FOYER 1 |  | 20 | Nos | 400000 | 0.8
d | Plate Heat Exchanger | Plate Heat Exchanger | AHU, V Fans, TFA, Plate Heat Exchanger | HVAC | EH 1 AND FOYER 1 |  | 2 | Nos | 5000000 | 1
e | CHW Pipes | CHW Pipes | CHW Pipes | HVAC | External Development Works |  | 1200 | MTS | 50000 | 6
| EH 2 AND FOYER 2 | [8 empty] | 8.77 | 7.5 | 0.26872
a | AHU | AHU | AHU, V Fans, TFA, Plate Heat Exchanger | HVAC | EH 2 AND FOYER 2 |  | 21 | Nos | 700000 | 1.47
b | V Fans | V Fans | AHU, V Fans, TFA, Plate Heat Exchanger | HVAC | EH 2 AND FOYER 2 |  | 20 | Nos | 250000 | 0.5
c | TFA | TFA | AHU, V Fans, TFA, Plate Heat Exchanger | HVAC | EH 2 AND FOYER 2 |  | 20 | Nos | 400000 | 0.8
d | Plate Heat Exchanger | Plate Heat Exchanger | AHU, V Fans, TFA, Plate Heat Exchanger | HVAC | EH 2 AND FOYER 2 |  | 2 | Nos | 5000000 | 1
e | CHW Pipes | CHW Pipes | CHW Pipes | HVAC | External Development Works |  | 1000 | MTS | 50000 | 5
| CONVENTION | [8 empty] | 13.835 | 11.06 | 0.39627
a | AHU | AHU | AHU, V Fans, TFA, Plate Heat Exchanger | HVAC | Convention Center |  | 53 | Nos | 700000 | 3.71
b | V Fans | V Fans | AHU, V Fans, TFA, Plate Heat Exchanger | HVAC | Convention Center |  | 25 | Nos | 250000 | 0.625
c | TFA | TFA | AHU, V Fans, TFA, Plate Heat Exchanger | HVAC | Convention Center |  | 25 | Nos | 400000 | 1
d | Plate Heat Exchanger | Plate Heat Exchanger | AHU, V Fans, TFA, Plate Heat Exchanger | HVAC | Convention Center |  | 3 | Nos | 5000000 | 1.5
e | CHW Pipes | CHW Pipes | CHW Pipes | HVAC | External Development Works |  | 1400 | MTS | 50000 | 7
| BSMT 3 | [8 empty] | 2.225 | 2.1 | 0.075242
a | V Fans | V Fans | V Fans, Pumps | HVAC | Exhibition Hall 3 |  | 25 | Nos | 250000 | 0.625
b | Pumps | Pumps | V Fans, Pumps | HVAC | Exhibition Hall 3 |  | 5 | Nos | 1000000 | 0.5
c | CHW Pipes | CHW Pipes | CHW Pipes | HVAC | External Development Works |  | 220 | MTS | 50000 | 1.1
| BSMT ADJACENT TO CC | [8 empty] | 2.75 | 2.74 | 0.098173
a | V Fans | V Fans | V Fans | HVAC | Basement Convention Center |  | 30 | Nos | 250000 | 0.75
b | CHW Pipes | CHW Pipes | CHW Pipes | HVAC | External Development Works |  | 400 | MTS | 50000 | 2
| ELECTRICAL SUBSTATION | [8 empty] | 2 | 1.8 | 0.064493
a | CHW Pipes | CHW Pipes | CHW Pipes | HVAC | External Development Works |  | 50 | MTS | 50000 | 0.25
| DG BUILDING | [8 empty] | 1.75 | 1.7 | 0.06091
a | V Fans | V Fans | V Fans | HVAC | DG BUILDING |  | 10 | Nos | 250000 | 0.25
b | CHW Pipes | CHW Pipes | CHW Pipes | HVAC | External Development Works |  | 300 | MTS | 50000 | 1.5
| PLANT ROOM AND GALLERY | [8 empty] | 17.6 | 19.15 | 0.68613
a | Chillar | Chillar | Chillar, Heat pumps | HVAC | Plant Room And Gallery |  | 6 | Nos | 26000000 | 15.6
b | Ring mains |  |  | HVAC | Plant Room And Gallery |  | 0 | MTS | 50000 | 0
c | Heat pumps | Heat pumps | Chillar, Heat pumps | HVAC | Plant Room And Gallery |  | 8 | Nos | 2500000 | 2
| SERVICE GALLERY |  |  |  | SERVICE GALLERY
a | Ring mains | Ring mains | Ring mains |  | SERVICE GALLERY |  | 160 | MTS | 50000 | 0.8 | 0.65 | 0.023289
| BSMT E 3 |  |  |  | Exhibition Hall 3
a | Transformer | Transformer | Transformer |  | Exhibition Hall 3 |  | 10000 | KVA | 1300 | 1.3 | 1.31 | 0.046937
EXTERNAL DEVELOPMENT WORKS
a | 66KV Transformer | 66KV Transformer | 66KV HT Panels, HT Cables, 66KV Transformer |  | External Development Works |  | 2 | Nos | 20000000 | 4 | 3.66 | 0.13114
DG BUILDING
a | Generator | Generators including Cooling Tower | Generators including Cooling Tower |  | DG BUILDING |  | 36000 | KVA | 8000 | 28.8 | 24.91 | 0.89251
b | Cooling tower | Generators including Cooling Tower | Generators including Cooling Tower |  | DG BUILDING |  | 14400 | TR | 700 | 1.008 | 1.22 | 0.043712
| ELECTRICAL EQUIPMENTS | [8 empty] | 24 | 20.29 | 0.72698
a | 66KV HT Panel | 66KV HT Panel | 66KV HT Panels, HT Cables, 66KV Transformer | ELECTRICAL EQUIPMENTS | External Development Works |  | 1 | Nos |  | 4
b | [6 empty] | 2 | Nos |  | 20
| SOLID WASTE | Pneumatic Solid Waste Management System | Pneumatic Solid Waste Management System |  | External Development Works |  |  |  |  | 35 | 3.07 | 0.11
| STP | STP | STP |  | External Development Works |  |  |  |  | 8 | 5.7 | 0.20423
| WTP | WTP | WTP |  | External Development Works |  |  |  |  | 0.5 | 0.28 | 0.010032
RETRACTABLE SEATING
| Convention | Retractable Seating | Retractible, Fixed Seating - Convention Centre |  | Special Items |  |  |  |  | 65.19 | 64.65 | 2.3164
| Exhibition halls | Retractable Seating | Retractible, Fixed Seating - Exhibition Hall |  | Special Items |  |  |  |  | 60.9 | 16.23 | 0.58151
| LED ON FAÇADE | LED on External Facade | LED on External Facade |  | Special Items |  | 8800 | SQM | 100000 | 88 | 88.18 | 3.1594
| SLIDING FOLDING | Sliding/Folding - Ver. Prtn. | Sliding/Folding - Ver. Prtn. |  | Special Items |  | 1 | Lot | PEAC | 23 | 19.03 | 0.68183
8 | GRC External
| Exhibition hall 1 | GRC Cladding & ACM | GRC Cladding & ACM |  | EH 1 AND FOYER 1 |  | 3929.8707 |  | 23500 | 9.2352 | 9.2352 |  | Composite Rate
| Exhibition hall 2 | GRC Cladding & ACM | GRC Cladding & ACM |  | EH 2 AND FOYER 2 |  | 5575.345 |  | 23500 | 13.1021 | 13.1021 |  | Composite Rate
| Convention center | GRC Cladding & ACM | GRC Cladding & ACM |  | Convention center |  | 6941.6245 |  | 23500 | 16.3128 | 16.3128 |  | Composite Rate
9 | GRC False Ceiling
| Exhibition hall 1 & GRAND FOYER | GRC False Ceiling | GRC False Ceiling |  | EH 1 AND FOYER 1 |  | 14215.79 |  | 7500 | 10.6618 | 10.6618
| Exhibition hall 2 & GRAND FOYER | GRC False Ceiling | GRC False Ceiling |  | EH 2 AND FOYER 2 |  | 24640 |  | 7500 | 18.48 | 18.48
| Convention center | GRC False Ceiling | GRC False Ceiling |  | Convention center |  | 11243.256 |  | 7500 | 8.4324 | 8.4324
10 | Fire Protection System
| Exhibition hall 1 & GRAND FOYER | Fire Protection System | Fire Protection System |  | EH 1 AND FOYER 1 |  | 11355.3 |  | 4000 | 4.5421
| Exhibition hall 2 & GRAND FOYER | Fire Protection System | Fire Protection System |  | EH 2 AND FOYER 2 |  | 9944.9 |  | 4000 | 3.978
| Convention center | Fire Protection System | Fire Protection System |  | Convention center |  | 11743.9 |  | 4000 | 4.6976
| Basement Convention Center | Fire Protection System | Fire Protection System |  | Basement Convention Center |  | 4442.8 |  | 4000 | 1.7771
| Exhibition Hall 3 | Fire Protection System | Fire Protection System |  | Exhibition Hall 3 |  | 5651.5 |  | 4000 | 2.2606
| DG yard | Fire Protection System | Fire Protection System |  | DG BUILDING |  | 1072 |  | 4000 | 0.4288
| ESS | Fire Protection System | Fire Protection System |  | ELECTRICAL SUBSTATION |  | 406.7 |  | 4000 | 0.16268
| Fire station | Fire Protection System | Fire Protection System |  | Fire Station |  | 136 |  | 4000 | 0.0544
| Guard room | Fire Protection System | Fire Protection System |  | Guard Room |  | 8.5 |  | 4000 | 0.0034
| Service gallery | Fire Protection System | Fire Protection System |  | SERVICE GALLERY |  | 6354.5 |  | 4000 | 2.5418
11 | PHE
| Exhibition hall 1 & GRAND FOYER | PHE Systems | PHE Systems |  | EH 1 AND FOYER 1 |  |  |  |  | 1.4675 | 1.4675
| Exhibition hall 2 & GRAND FOYER | PHE Systems | PHE Systems |  | EH 2 AND FOYER 2 |  |  |  |  | 2.755 | 2.755
| Convention center | PHE Systems | PHE Systems |  | Convention center |  |  |  |  | 2.11 | 2.11
12 | STRUCTURAL STEEL WORKS
| Exhibition Hall No. 1 & Ramp | Structural Steel Works | Structural Steel, Roofing, Reinforcement Steel, Safety Material |  | EH 1 AND FOYER 1 |  | 5787.087 | MT | 50000 | 28.9354 |  |  | 145.9615
| Exhibition Hall No. 2 | Structural Steel Works | Structural Steel, Roofing, Reinforcement Steel, Safety Material |  | EH 2 AND FOYER 2 |  | 5482.8959 | MT | 50000 | 27.4145 |  |  | 138.2892
| Foyer including Basement in front of Exhibition Hall No. 1 | Structural Steel Works | Structural Steel, Roofing, Reinforcement Steel, Safety Material |  | EH 1 AND FOYER 1 |  | 5498.5732 | MT | 50000 | 27.4929 |  |  | 138.6846
| Foyer including Basement in front of Exhibition Hall No. 2 | Structural Steel Works | Structural Steel, Roofing, Reinforcement Steel, Safety Material |  | EH 2 AND FOYER 2 |  | 5311.4969 | MT | 50000 | 26.5575 |  |  | 133.9662
| Convention Centre | Structural Steel Works | Structural Steel, Roofing, Reinforcement Steel, Safety Material |  | Convention Center |  | 8319.9469 | MT | 50000 | 41.5997 |  |  | 209.8451
[10 empty] | 152 |  |  | 766.7467
13 | Roofing Works
| Exhibition Hall No. 1 & Ramp | Roofing Works | Structural Steel, Roofing, Reinforcement Steel, Safety Material |  | EH 1 AND FOYER 1 |  | 20349.9868 | Sqm | 2800 | 5.698 |  |  | 145.9615 | #DIV/0!
| Exhibition Hall No. 2 | Roofing Works | Structural Steel, Roofing, Reinforcement Steel, Safety Material |  | EH 2 AND FOYER 2 |  | 19280.315 | Sqm | 2800 | 5.3985 |  |  | 138.2892
| Foyer including Basement in front of Exhibition Hall No. 1 | Roofing Works | Structural Steel, Roofing, Reinforcement Steel, Safety Material |  | EH 1 AND FOYER 1 |  | 19335.4434 | Sqm | 2800 | 5.4139 |  |  | 138.6846
| Foyer including Basement in front of Exhibition Hall No. 2 | Roofing Works | Structural Steel, Roofing, Reinforcement Steel, Safety Material |  | EH 2 AND FOYER 2 |  | 18677.5994 | Sqm | 2800 | 5.2297 |  |  | 133.9662
| Convention Centre | Roofing Works | Structural Steel, Roofing, Reinforcement Steel, Safety Material |  | Convention Center |  | 29256.6554 | Sqm | 2800 | 8.1919 |  |  | 209.8451
[10 empty] | 29.932 |  |  | 766.7467
14 | REINFORCEMENT STEEL
| Exhibition Hall No. 1 & Ramp | Reinforcement Steel | Structural Steel, Roofing, Reinforcement Steel, Safety Material |  | EH 1 AND FOYER 1 |  | 5006.018 | MT | 35000 | 17.5211 |  |  | 145.9615
| Exhibition Hall No. 2 | Reinforcement Steel | Structural Steel, Roofing, Reinforcement Steel, Safety Material |  | EH 2 AND FOYER 2 |  | 4742.8829 | MT | 35000 | 16.6001 |  |  | 138.2892
| Foyer including Basement in front of Exhibition Hall No. 1 | Reinforcement Steel | Structural Steel, Roofing, Reinforcement Steel, Safety Material |  | EH 1 AND FOYER 1 |  | 4756.4442 | MT | 35000 | 16.6476 |  |  | 138.6846
| Foyer including Basement in front of Exhibition Hall No. 2 | Reinforcement Steel | Structural Steel, Roofing, Reinforcement Steel, Safety Material |  | EH 2 AND FOYER 2 |  | 4594.6172 | MT | 35000 | 16.0812 |  |  | 133.9662
| Convention Centre | Reinforcement Steel | Structural Steel, Roofing, Reinforcement Steel, Safety Material |  | Convention Center |  | 7197.024 | MT | 35000 | 25.1896 |  |  | 209.8451
| Exhibition hall -3 ( basement ) | Reinforcement Steel | Reinforcement |  | Exhibition Hall 3 |  | 2959.2639 | MT | 35000 | 10.3574 |  |  | 86.2839
| Basement adjacent to Convention Centre | Reinforcement Steel | Reinforcement |  | Basement Convention Center |  | 1394.7207 | MT | 35000 | 4.8815 |  |  | 40.6662
| Electrical Substation | Reinforcement Steel | Reinforcement |  | ELECTRICAL SUBSTATION |  | 219.6556 | MT | 35000 | 0.76879 |  |  | 6.4045
| DG Building | Reinforcement Steel | Reinforcement |  | DG BUILDING |  | 714.5394 | MT | 35000 | 2.5009 |  |  | 20.834
| Fire Station & Disaster Management Building including Medical Centre | Reinforcement Steel | Reinforcement |  | Fire Station |  | 47.9613 | MT | 35000 | 0.16786 |  |  | 1.3984
| Service Gallery | Reinforcement Steel | Reinforcement |  | SERVICE GALLERY |  | 2963.873 | MT | 35000 | 10.3736 |  |  | 86.4183
[10 empty] | 121.0895 |  |  | 1008.7519
15 | Safety Equipments
| Exhibition Hall No. 1 | Safety Equipments | Structural Steel, Roofing, Reinforcement Steel, Safety Material |  | EH 1 AND FOYER 1 |  | 1 | LS | 2.9192 | 2.9192
| Exhibition Hall No. 2 | Safety Equipments | Structural Steel, Roofing, Reinforcement Steel, Safety Material |  | EH 2 AND FOYER 2 |  | 1 | LS | 2.7658 | 2.7658
| Foyer including Basement in front of Exhibition Hall No. 1 | Safety Equipments | Structural Steel, Roofing, Reinforcement Steel, Safety Material |  | EH 1 AND FOYER 1 |  | 1 | LS | 1.3868 | 1.3868
| Foyer including Basement in front of Exhibition Hall No. 2 | Safety Equipments | Structural Steel, Roofing, Reinforcement Steel, Safety Material |  | EH 2 AND FOYER 2 |  | 1 | LS | 1.3397 | 1.3397
| Convention Centre | Safety Equipments | Structural Steel, Roofing, Reinforcement Steel, Safety Material |  | Convention Center |  | 1 | LS | 2.0985 | 2.0985
10.51
|  |  | 248000000 | [7 empty] | 571.004 | 20.4588

## GRC
DETAILED QUANTITIES - ECC DWARKA
S.NO | DESCRIPTION | NOS | LENGTH | BREADTH | HEIGHT | ADD | DEDUCT | REFERENCE | DRAWING NO. | USED FOR
1 | GRC PANELS
Exhibition hall 1
| North east façade elevations | 3 | 8 |  | 15.08 | 361.92 |  | North east side elevation | E1 - X - XX - 400 - 06 | GRC
|  | 1 | 4.65 |  | 8 | 37.2 |  | North east side elevation | E1 - X - XX - 400 - 06 | GRC
| North west side elevation | 1 | 4.63 |  | 14 | 64.82 |  | North west side elevation | E1 - X - XX - 401 - 06 | GRC
|  | 3 | 8 |  | 22.36 | 536.64 |  | North west side elevation | E1 - X - XX - 401 - 06 | GRC
|  | 2 | 72 |  | 7.01 | 1009.44 |  | North west side elevation | E1 - X - XX - 401 - 06 | GRC
|  | 0.5 | 3.94 |  | 6.31 | 12.4307 |  | North west side elevation | E1 - X - XX - 401 - 06 | GRC
| South west side elevation | 4 | 8 |  | 15.4 | 492.8 |  | South west side elevation | E1 - X - XX - 402 - 06 | GRC
|  | 1 | 200.26 |  | 7 | 1401.82 |  | South west side elevation | E1 - X - XX - 402 - 06 | GRC
|  | 0.5 | 4 |  | 6.4 | 12.8 |  | South west side elevation | E1 - X - XX - 402 - 06 | GRC
| SUB TOTAL |  |  |  |  | 3929.8707 |  |  |  |  | 23500
Exhibition hall 2
| North east façade elevations | 3 | 8 |  | 15.08 | 361.92 |  | North west side elevation | E2 - X - XX - 400 - 06 | GRC
|  | 1 | 4 |  | 7 | 28 |  | North west side elevation | E2 - X - XX - 400 - 06 | GRC
|  | 1 | 168 |  | 7 | 1176 |  | North west side elevation | E2 - X - XX - 400 - 06 | GRC
| North east façade elevations | 3 | 8 |  | 15.08 | 361.92 |  | North east side elevation | E2 - X - XX - 401 - 06 | GRC
|  | 1 | 200 |  | 7 | 1400 |  | North east side elevation | E2 - X - XX - 401 - 06 | GRC
|  | 0.5 | 4.27 |  | 7 | 14.945 |  | North east side elevation | E2 - X - XX - 401 - 06 | GRC
| South west side elevation | 4 | 8 |  | 15.08 | 482.56 |  | South west side elevation | E2 - X - XX - 402 - 06 | GRC
|  | 1 | 248 |  | 7 | 1736 |  | South west side elevation | E2 - X - XX - 402 - 06 | GRC
|  | 0.5 | 4 |  | 7 | 14 |  | South west side elevation | E2 - X - XX - 402 - 06 | GRC
| SUB TOTAL |  |  |  |  | 5575.345
Convention center
| North west façade elevations | 1 | 120 |  | 9.3 | 1116 |  | CC Elevations | CC - X - XX - 400 - 07 | GRC
|  | 1 | 68.1 |  | 9.3 | 633.33 |  | CC Elevations | CC - X - XX - 400 - 07 | GRC
|  | 1 | 30 |  | 9.3 | 279 |  | CC Elevations | CC - X - XX - 400 - 07 | GRC
|  | 1 | 28 |  | 14 | 392 |  | CC Elevations | CC - X - XX - 400 - 07 | GRC
|  | 1 | 40 |  | 9.3 | 372 |  | CC Elevations | CC - X - XX - 400 - 07 | GRC
|  | 1 | 3.4 |  | 11.4 | 38.76 |  | CC Elevations | CC - X - XX - 400 - 07 | GRC
|  | 1 | 3.4 |  | 9.95 | 33.83 |  | CC Elevations | CC - X - XX - 400 - 07 | GRC
|  | 1 | 3.4 |  | 8.75 | 29.75 |  | CC Elevations | CC - X - XX - 400 - 07 | GRC
|  | 1 | 3.4 |  | 6.75 | 22.95 |  | CC Elevations | CC - X - XX - 400 - 07 | GRC
|  | 1 | 6.75 |  | 2.15 | 14.5125 |  | CC Elevations | CC - X - XX - 400 - 07 | GRC
| South east façade elevations | 2 | 20.25 |  | 4.65 | 188.325 |  | CC Elevations | CC - X - XX - 400 - 07 | GRC
|  | 1 | 71.65 |  | 9.3 | 666.345 |  | CC Elevations | CC - X - XX - 400 - 07 | GRC
|  | 1 | 21.88 |  | 4.65 | 101.742 |  | CC Elevations | CC - X - XX - 400 - 07 | GRC
|  | 1 | 16 |  | 4.75 | 76 |  | CC Elevations | CC - X - XX - 400 - 07 | GRC
|  | 1 | 7.5 |  | 4.65 | 34.875 |  | CC Elevations | CC - X - XX - 400 - 07 | GRC
|  | 1 | 77.15 |  | 9.3 | 717.495 |  | CC Elevations | CC - X - XX - 400 - 07 | GRC
|  | 1 | 7.5 |  | 4.65 | 34.875 |  | CC Elevations | CC - X - XX - 400 - 07 | GRC
|  | 1 | 3.4 |  | 11.4 | 38.76 |  | CC Elevations | CC - X - XX - 400 - 07 | GRC
|  | 1 | 3.4 |  | 9.95 | 33.83 |  | CC Elevations | CC - X - XX - 400 - 07 | GRC
|  | 1 | 3.4 |  | 8.75 | 29.75 |  | CC Elevations | CC - X - XX - 400 - 07 | GRC
|  | 1 | 3.4 |  | 6.75 | 22.95 |  | CC Elevations | CC - X - XX - 400 - 07 | GRC
|  | 1 | 6.75 |  | 2.15 | 14.5125 |  | CC Elevations | CC - X - XX - 400 - 07 | GRC
| North east façade elevations | 2 | 40.85 |  | 9.3 | 759.81 |  | CC Elevations | CC - X - XX - 401 - 07 | GRC
|  | 1 | 31.75 |  | 4.65 | 147.6375 |  | CC Elevations | CC - X - XX - 401 - 07 | GRC
|  | 1 | 81.15 |  | 4.65 | 377.3475 |  | CC Elevations | CC - X - XX - 401 - 07 | GRC
|  | 1 | 9 |  | 4 | 36 |  | CC Elevations | CC - X - XX - 401 - 07 | GRC
|  | 1 | 2.45 |  | 4.65 | 11.3925 |  | CC Elevations | CC - X - XX - 401 - 07 | GRC
|  | 0.5 | 8.5 |  | 4 | 17 |  | CC Elevations | CC - X - XX - 401 - 07 | GRC
|  | 1 | 32.3 |  | 4.65 | 150.195 |  | CC Elevations | CC - X - XX - 401 - 07 | GRC
|  | 1 | 33 |  | 4.65 | 153.45 |  | CC Elevations | CC - X - XX - 401 - 07 | GRC
| South west façade elevations | 1 | 8 |  | 4.65 | 37.2 |  | CC Elevations | CC - X - XX - 402 - 07 | GRC
|  | 3 | 8 |  | 15 | 360 |  | CC Elevations | CC - X - XX - 402 - 07 | GRC
| SUB TOTAL |  |  |  |  | 6941.6245
Exhibition hall 1 & GRAND FOYER
| False ceiling CE .09 V016 - V017 TO H026 - H027 | 2 | 39.7 |  | 8.4 | 666.96 |  | CEILING FINISHES GF | E1 - X - F0 - 620 - 07 | GRC
| False ceiling CE .09 V016 - V017 TO H026 - H027 | 2 | 31.7 |  | 3.77 | 239.018 |  | CEILING FINISHES GF | E1 - X - F0 - 620 - 07 | GRC
| False ceiling CE .09 V017 - V026 TO H07 | 1 | 71.5 |  | 8.5 | 607.75 |  | CEILING FINISHES GF | E1 - X - F0 - 620 - 07 | GRC
| False ceiling CE .09 V027 - V036 TO H07 | 1 | 72.145 |  | 4.2 | 303.009 |  | CEILING FINISHES GF | E1 - X - F0 - 620 - 07 | GRC
| False ceiling CE .09 V027 - V036 TO H07 | 2 | 7.8 |  | 4.4 | 68.64 |  | CEILING FINISHES GF | E1 - X - F0 - 620 - 07 | GRC
| False ceiling CE .09 V037 - V050 TO H07 | 1 | 15.68 |  | 8.4 | 131.712 |  | CEILING FINISHES GF | E1 - X - F0 - 620 - 07 | GRC
| False ceiling CE .09 V037 - V050 TO H07 | 1 | 8 |  | 4.16 | 33.28 |  | CEILING FINISHES GF | E1 - X - F0 - 620 - 07 | GRC
| False ceiling CE .09 V037 - V050 TO H07 | 1 | 8 |  | 4.5 | 36 |  | CEILING FINISHES GF | E1 - X - F0 - 620 - 07 | GRC
| False ceiling CE .09 V037 - V050 TO H07 | 1 | 63.62 |  | 8.3 | 528.046 |  | CEILING FINISHES GF | E1 - X - F0 - 620 - 07 | GRC
| False ceiling CE .09 V046 - V050 TO H07 - H08 | 1 | 32 |  | 8.5 | 272 |  | CEILING FINISHES GF | E1 - X - F0 - 620 - 07 | GRC
| False ceiling CE .09 V046 - V047 TO H08 - H014 | 1 | 48 |  | 8.5 | 408 |  | CEILING FINISHES GF | E1 - X - F0 - 620 - 07 | GRC
| False ceiling CE .09 V046 - V047 TO H014 - H015 | 1 | 8 |  | 4 | 32 |  | CEILING FINISHES GF | E1 - X - F0 - 620 - 07 | GRC
| False ceiling CE .09 V046 - V050 TO H015 - H020 | 1 | 27 |  | 40 | 1080 |  | CEILING FINISHES GF | E1 - X - F0 - 620 - 07 | GRC
| False ceiling CE .09 V046 - V047 TO H020 - H021 | 1 | 8 |  | 4 | 32 |  | CEILING FINISHES GF | E1 - X - F0 - 620 - 07 | GRC
| False ceiling CE .09 V046 - V047 TO H021 - H026 | 1 | 40 |  | 8 | 320 |  | CEILING FINISHES GF | E1 - X - F0 - 620 - 07 | GRC
| False ceiling CE .09 V041 - V047 TO H027 ONWARDS | 13 | 8 |  | 8 | 832 |  | CEILING FINISHES GF | E1 - X - F0 - 620 - 07 | GRC
| False ceiling CE .09 V017 - V039 TO H027 - H026 | 18.5 | 8 |  | 8 | 1184 |  | CEILING FINISHES GF | E1 - X - F0 - 620 - 07 | GRC
| False ceiling CE .09 V016 - V017 TO H026 - H027 | 2 | 39.7 |  | 8.4 | 666.96 |  | CEILING FINISHES SF | E1 - X - F2 - 620 - 07 | GRC
| False ceiling CE .09 V016 - V017 TO H026 - H027 | 2 | 31.7 |  | 3.77 | 239.018 |  | CEILING FINISHES SF | E1 - X - F2 - 620 - 07 | GRC
| False ceiling CE .09 V017 - V026 TO H07 | 1 | 71.5 |  | 8.5 | 607.75 |  | CEILING FINISHES SF | E1 - X - F2 - 620 - 07 | GRC
| False ceiling CE .09 V027 - V036 TO H07 | 1 | 72.145 |  | 4.2 | 303.009 |  | CEILING FINISHES SF | E1 - X - F2 - 620 - 07 | GRC
| False ceiling CE .09 V027 - V036 TO H07 | 2 | 7.8 |  | 4.4 | 68.64 |  | CEILING FINISHES SF | E1 - X - F2 - 620 - 07 | GRC
| False ceiling CE .09 V037 - V050 TO H07 | 1 | 15.68 |  | 8.4 | 131.712 |  | CEILING FINISHES SF | E1 - X - F2 - 620 - 07 | GRC
| False ceiling CE .09 V037 - V050 TO H07 | 1 | 8 |  | 4.16 | 33.28 |  | CEILING FINISHES SF | E1 - X - F2 - 620 - 07 | GRC
| False ceiling CE .09 V037 - V050 TO H07 | 1 | 8 |  | 4.5 | 36 |  | CEILING FINISHES SF | E1 - X - F2 - 620 - 07 | GRC
| False ceiling CE .09 V037 - V050 TO H07 | 1 | 63.62 |  | 8.3 | 528.046 |  | CEILING FINISHES SF | E1 - X - F2 - 620 - 07 | GRC
| False ceiling CE .09 V046 - V050 TO H07 - H08 | 1 | 32 |  | 8.5 | 272 |  | CEILING FINISHES SF | E1 - X - F2 - 620 - 07 | GRC
| False ceiling CE .09 V046 - V047 TO H08 - H014 | 1 | 48 |  | 8.5 | 408 |  | CEILING FINISHES SF | E1 - X - F2 - 620 - 07 | GRC
| False ceiling CE .09 V046 - V047 TO H014 - H015 | 1 | 8 |  | 4 | 32 |  | CEILING FINISHES SF | E1 - X - F2 - 620 - 07 | GRC
| False ceiling CE .09 V046 - V050 TO H015 - H020 | 1 | 27 |  | 40 | 1080 |  | CEILING FINISHES SF | E1 - X - F2 - 620 - 07 | GRC
| False ceiling CE .09 V046 - V047 TO H020 - H021 | 1 | 8 |  | 4 | 32 |  | CEILING FINISHES SF | E1 - X - F2 - 620 - 07 | GRC
| False ceiling CE .09 V046 - V047 TO H021 - H026 | 1 | 40 |  | 8 | 320 |  | CEILING FINISHES SF | E1 - X - F2 - 620 - 07 | GRC
| False ceiling CE .09 V041 - V047 TO H027 ONWARDS | 13 | 8 |  | 8 | 832 |  | CEILING FINISHES SF | E1 - X - F2 - 620 - 07 | GRC
| False ceiling CE .09 V017 - V039 TO H027 - H026 | 18.5 | 8 |  | 8 | 1184 |  | CEILING FINISHES SF | E1 - X - F2 - 620 - 07 | GRC
| False ceiling CE .09 V016 - V017 TO H026 - H027 | 2 | 39.7 |  | 8.4 | 666.96 |  | CEILING FINISHES SF | E1 - X - F2 - 620 - 07 | GRC
| SUB TOTAL |  |  |  |  | 14215.79
Exhibition hall 2 & GRAND FOYER
| False ceiling CE .09 V016 - V017 TO H031 - H052 | 14 | 8 |  | 8 | 896 |  | CEILING FINISHES GF | E2 - X - F0 - 620 - 07 | GRC
| False ceiling CE .09 V016 - V050 TO H026 - H032 | 64 | 8 |  | 8 | 4096 |  | CEILING FINISHES GF | E2 - X - F0 - 620 - 07 | GRC
| False ceiling CE .09 V041 - V047 TO H036 - H051 | 64 | 8 |  | 8 | 4096 |  | CEILING FINISHES GF | E2 - X - F0 - 620 - 07 | GRC
| False ceiling CE .09 V017 - V046 TO H051 - H052 | 26 | 8 |  | 8 | 1664 |  | CEILING FINISHES GF | E2 - X - F0 - 620 - 07 | GRC
| False ceiling CE .09 V042 - V047 TO H036 - H047 | 28 | 8 |  | 8 | 1792 |  | CEILING FINISHES FF | E2 - X - F1 - 620 - 07 | GRC
| False ceiling CE .09 V017 - V047 TO H026 - H032 | 69 | 8 |  | 8 | 4416 |  | CEILING FINISHES FF | E2 - X - F1 - 620 - 07 | GRC
| False ceiling CE .09 V36 - V047 TO H032 - H052 | 84 | 8 |  | 8 | 5376 |  | CEILING FINISHES SF | E2 - X - F2 - 620 - 07 | GRC
| False ceiling CE .09 V16 - V036 TO H051 - H052 | 18 | 8 |  | 8 | 1152 |  | CEILING FINISHES SF | E2 - X - F2 - 620 - 07 | GRC
| False ceiling CE .09 V16 - V017 TO H032 - H051 | 18 | 8 |  | 8 | 1152 |  | CEILING FINISHES SF | E2 - X - F2 - 620 - 07 | GRC
| SUB TOTAL |  |  |  |  | 24640
Convention center
| False ceiling CE .09 | 1 | 4.6 |  | 15.46 | 71.116 |  | CEILING FINISHES GF | CC - X - F0 - 630 - 07 | GRC
| False ceiling CE .09 | 1 | 1.2 |  | 1.2 | 1.44 |  | CEILING FINISHES GF | CC - X - F0 - 630 - 07 | GRC
| False ceiling CE .09 | 1 | 48 |  | 0.9 | 43.2 |  | CEILING FINISHES GF | CC - X - F0 - 630 - 07 | GRC
| False ceiling CE .09 | 0.75 | 85 |  | 34 | 2167.5 |  | CEILING FINISHES GF | CC - X - F0 - 630 - 07 | GRC
| False ceiling CE .09 | 19 | 8 |  | 8 | 1216 |  | CEILING FINISHES FF | CC - X - F1 - 630 - 07 | GRC
| False ceiling CE .09 | 13.5 | 8 |  | 8 | 864 |  | CEILING FINISHES SF | CC - X - F2 - 630 - 07 | GRC
| False ceiling CE .09 | 44 | 8 |  | 8 | 2816 |  | CEILING FINISHES TF | CC - X - F3 - 630 - 07 | GRC
| False ceiling CE .09 | 21 | 8 |  | 8 | 1344 |  | CEILING FINISHES FF | CC - X - F4 - 630 - 07 | GRC
| False ceiling CE .09 | 19 | 8 |  | 8 | 1216 |  | CEILING FINISHES FF | CC - X - F5 - 630 - 07 | GRC
| False ceiling CE .09 | 23.5 | 8 |  | 8 | 1504 |  | CEILING FINISHES GF | CC - X - F7 - 630 - 07 | GRC
| SUB TOTAL |  |  |  |  | 11243.256
| GRAND TOTAL |  |  |  |  | 66545.8862

## LED SCREEN
DETAILED QUANTITIES - ECC DWARKA
S.NO | DESCRIPTION | NOS | LENGTH | BREADTH | HEIGHT | ADD | DEDUCT | REFERENCE | DRAWING NO. | USED FOR
4 | LED SCREEN
Convention center
| North west façade elevations | 1 | 135 |  | 21 | 2835 |  | CC Elevations | CC - X - XX - 400 - 07 | LED
| South east façade elevations | 1 | 135 |  | 21 | 2835 |  | CC Elevations | CC - X - XX - 400 - 07 | LED
| North east façade elevations | 1 | 88.5 |  | 21 | 1858.5 |  | CC Elevations | CC - X - XX - 401 - 07 | LED
| South west façade elevations | 1 | 88.5 |  | 21 | 1858.5 |  | CC Elevations | CC - X - XX - 402 - 07 | LED
| GRAND TOTAL |  |  |  |  | 9387

## DGU
DETAILED QUANTITIES - ECC DWARKA
S.NO | DESCRIPTION | NOS | LENGTH | BREADTH | HEIGHT | ADD | DEDUCT | REFERENCE | DRAWING NO. | USED FOR
3 | DOUBLE GLASS GLAZING
Exhibition hall 1
| North east façade elevations | 1 | 47.75 |  | 15 | 716.25 |  | North east side elevation | E1 - X - XX - 400 - 06 | DGU
|  | 1 | 24 |  | 5.8 | 139.2 |  | North east side elevation | E1 - X - XX - 400 - 06 | DGU
|  | 2 | 72 |  | 5.8 | 835.2 |  | North east side elevation | E1 - X - XX - 400 - 06 | DGU
| North west side elevation | 2 | 72 |  | 5.8 | 835.2 |  | North west side elevation | E1 - X - XX - 401 - 06 | DGU
| South west side elevation | 2 | 72 |  | 5.8 | 835.2 |  | South west side elevation | E1 - X - XX - 402 - 06 | DGU
|  | 1 | 104 |  | 15 | 1560 |  | South west side elevation | E1 - X - XX - 402 - 06 | DGU
| SUB TOTAL |  |  |  |  | 4921.05
Exhibition hall 2
| North west façade elevations | 2 | 72 |  | 5.8 | 835.2 |  | North west side elevation | E2 - X - XX - 400 - 06 | DGU
| North east façade elevations | 2 | 72 |  | 5.8 | 835.2 |  | North east side elevation | E2 - X - XX - 401 - 06 | DGU
| South west side elevation & Foyer | 2 | 72 |  | 5.8 | 835.2 |  | South west side elevation | E2 - X - XX - 402 - 06 | DGU
|  | 2 | 32 |  | 15 | 960 |  | South west side elevation | E2 - X - XX - 402 - 06 | DGU
[8 empty] | South west side elevation | E2 - X - XX - 402 - 06 | DGU
| SUB TOTAL |  |  |  |  | 3465.6
Convention center
| North west façade elevations | 1 | 100 |  | 4.65 | 465 |  | CC Elevations | CC - X - XX - 400 - 07 | DGU
|  | 1 | 25.5 |  | 9.25 | 235.875 |  | CC Elevations | CC - X - XX - 400 - 07 | DGU
| South east façade elevations | 1 | 20.8 |  | 9.37 | 194.896 |  | CC Elevations | CC - X - XX - 400 - 07 | DGU
| South east façade elevations | 1 | 11.21 |  | 6.48 | 72.6408 |  | CC Elevations | CC - X - XX - 400 - 07 | DGU
| South east façade elevations | 1 | 21 |  | 4.5 | 94.5 |  | CC Elevations | CC - X - XX - 400 - 07 | DGU
| South east façade elevations | 1 | 21 |  | 4.5 | 94.5 |  | CC Elevations | CC - X - XX - 400 - 07 | DGU
| South east façade elevations | 1 | 58 |  | 6.25 | 362.5 |  | CC Elevations | CC - X - XX - 400 - 07 | DGU
| North east façade elevations | 2 | 8 |  | 9.5 | 152 |  | CC Elevations | CC - X - XX - 401 - 07 | DGU
| South west façade elevations | 1 | 73 |  | 4.65 | 339.45 |  | CC Elevations | CC - X - XX - 402 - 07 | DGU
| SUB TOTAL |  |  |  |  | 2011.3618
| GRAND TOTAL |  |  |  |  | 10398.0118

## ACP
DETAILED QUANTITIES - ECC DWARKA
S.NO | DESCRIPTION | NOS | LENGTH | BREADTH | HEIGHT | ADD | DEDUCT | REFERENCE | DRAWING NO. | USED FOR
2 | ACP
Exhibition hall 1
| North east façade elevations | 1 | 24 |  | 9.17 | 220.08 |  | North east side elevation | E1 - X - XX - 400 - 06 | COPPER SLATS
|  | 2 | 72 |  | 9.17 | 1320.48 |  | North east side elevation | E1 - X - XX - 400 - 06 | COPPER SLATS
| Less doors | 4 | 8 |  | 6.5 |  | 208 | North east side elevation | E1 - X - XX - 400 - 06 | COPPER SLATS
| North west side elevation | 2 | 72 |  | 9.25 | 1332 |  | North west side elevation | E1 - X - XX - 401 - 06 | COPPER SLATS
| Less doors | 4 | 8 |  | 6.5 |  | 208 | North east side elevation | E1 - X - XX - 400 - 06 | COPPER SLATS
| South west side elevation & Foyer | 1 | 72 |  | 9.25 | 666 |  | South west side elevation | E1 - X - XX - 402 - 06 | COPPER SLATS
|  | 1 | 56 |  | 9.25 | 518 |  | South west side elevation | E1 - X - XX - 402 - 06 | COPPER SLATS
|  | 1 | 16 |  | 2.75 | 44 |  | South west side elevation | E1 - X - XX - 402 - 06 | COPPER SLATS
|  | 1 | 4.5 |  | 9 | 40.5 |  | South west side elevation | E1 - X - XX - 402 - 06 | COPPER SLATS
| Less doors | 4 | 8 |  | 6.5 |  | 208 | North east side elevation | E1 - X - XX - 400 - 06 | COPPER SLATS
[6 empty] | 4141.06 | 624
| SUB TOTAL |  |  |  |  | 3517.06
Exhibition hall 2
| North west façade elevations | 2 | 72 |  | 9.25 | 1332 |  | North west side elevation | E2 - X - XX - 400 - 06 | COPPER SLATS
| Less doors | 4 | 8 |  | 6.5 |  | 208 | North east side elevation | E1 - X - XX - 400 - 06 | COPPER SLATS
| North east façade elevations | 2 | 72 |  | 9.25 | 1332 |  | North east side elevation | E2 - X - XX - 401 - 06 | COPPER SLATS
|  | 4 | 8 |  | 6.5 |  | 208 | North east side elevation | E2 - X - XX - 401 - 06 | COPPER SLATS
| South west side elevation & Foyer | 2 | 72 |  | 9.25 | 1332 |  | South west side elevation | E2 - X - XX - 402 - 06 | COPPER SLATS
|  | 1 | 4.5 |  | 9.25 | 41.625
| Less doors | 4 | 8 |  | 6.5 |  | 208 | South west side elevation | E2 - X - XX - 402 - 06 | COPPER SLATS
[6 empty] | 4037.625 | 624 | South west side elevation | E2 - X - XX - 402 - 06 | COPPER SLATS
| SUB TOTAL |  |  |  |  | 3413.625
| GRAND TOTAL |  |  |  |  | 6930.685

## FIRE
DETAILED QUANTITIES - ECC DWARKA
FIRE FIGHTING SYSTEM
S.NO | DESCRIPTION | AREA | PENDENT | UPRIGHT | TOTAL | COST
CONVENTION CENTER
| Basement 1 | 13979 | 1397.9 | 0 | 1397.9 | 5591600
| Basement 2 | 10672 | 1067.2 | 0 | 1067.2 | 4268800
| Ground floor | 19225 | 1922.5 | 1922.5 | 3845 | 7690000
| First floor | 12323 | 1232.3 | 1232.3 | 2464.6 | 4929200
| Second floor | 11673 | 1167.3 | 1167.3 | 2334.6 | 4669200
| Third floor | 8851 | 885.1 | 885.1 | 1770.2 | 3540400
| Fourth floor | 8712 | 871.2 | 871.2 | 1742.4 | 3484800
| Fifth floor | 10220 | 1022 | 1022 | 2044 | 4088000
| Sixth floor | 8712 | 871.2 | 871.2 | 1742.4 | 3484800
| Seventh floor | 8715 | 871.5 | 871.5 | 1743 | 3486000
| Eigth floor | 4357 | 435.7 | 435.7 | 871.4 | 1742800
| SUB TOTAL | 117439 | 11743.9 | 9278.8 | 21022.7 | 46975600
BASEMENT ADJACENT TO CONVENTION CENTER
| Basement 1 | 11073 | 1107.3 | 0 | 1107.3 | 4429200
| Basement 2 | 11485 | 1148.5 | 0 | 1148.5 | 4594000
| Basement 3 | 10935 | 1093.5 | 0 | 1093.5 | 4374000
| Basement 4 | 10935 | 1093.5 | 0 | 1093.5 | 4374000
| SUB TOTAL | 44428 | 4442.8 | 0 | 4442.8 | 17771200
EXHIBITION HALL 1 AND FOYER 1
| Ground floor | 36852 | 3685.2 | 3685.2 | 7370.4 | 14740800
| First floor | 3229 | 322.9 | 322.9 | 645.8 | 1291600
| Second floor | 776 | 77.6 | 77.6 | 155.2 | 310400
| Foyer GF | 14085 | 1408.5 | 1408.5 | 2817 | 5634000
| Foyer FF | 1285 | 128.5 | 128.5 | 257 | 514000
| SUB TOTAL | 56227 | 5622.7 | 5622.7 | 11245.4 | 22490800
BASEMENTS FOYER 1
| Basement 1 | 21658 | 2165.8 | 0 | 2165.8 | 8663200
| Basement 2 | 17834 | 1783.4 | 0 | 1783.4 | 7133600
| Basement 3 | 17834 | 1783.4 | 0 | 1783.4 | 7133600
| SUB TOTAL | 57326 | 5732.6 | 0 | 5732.6 | 22930400
EXHIBITION HALL 2 AND FOYER 2
| Ground floor | 32372 | 3237.2 | 3237.2 | 6474.4 | 12948800
| First floor | 718 | 71.8 | 71.8 | 143.6 | 287200
| Mezzanine floor | 718 | 71.8 | 71.8 | 143.6 | 287200
| Foyer GF | 15247 | 1524.7 | 1524.7 | 3049.4 | 6098800
| SUB TOTAL | 49055 | 4905.5 | 4905.5 | 9811 | 19622000
BASEMENTS FOYER 2
| Basement 1 | 19004 | 1900.4 | 0 | 1900.4 | 7601600
| Basement 2 | 15695 | 1569.5 | 0 | 1569.5 | 6278000
| Basement 3 | 15695 | 1569.5 | 0 | 1569.5 | 6278000
| SUB TOTAL | 50394 | 5039.4 | 0 | 5039.4 | 20157600
EXHIBITION HALL 3
| Basement 1 | 27929 | 2792.9 | 0 | 2792.9 | 11171600
| Basement 2 | 28586 | 2858.6 | 0 | 2858.6 | 11434400
| SUB TOTAL | 56515 | 5651.5 | 0 | 5651.5 | 22606000
MISCELLANEOUS BUILDINGS
| DG yard | 10720 | 1072 | 0 | 1072 | 4288000
| ESS | 4067 | 406.7 | 0 | 406.7 | 1626800
| Fire station | 1360 | 136 | 0 | 136 | 544000
| Guard room | 17 | 8.5 | 8.5 | 17 | 34000
| Service gallery | 63545 | 6354.5 | 0 | 6354.5 | 25418000
| SUB TOTAL | 79709 | 7977.7 | 8.5 | 7986.2 | 31910800
GRAND TOTAL | [5 empty] | 204464400
TOTAL PENDENT | [5 empty] | 51116.1
TOTAL UPRIGHT | [5 empty] | 19815.5
TOTAL SPRINKLER | [5 empty] | 70931.6
TOTAL AREA | [5 empty] | 511093

## PHE
DETAILED QUANTITIES - ECC DWARKA
PUBLIC HEALTH ENGINEERING - PHE
S.NO | DESCRIPTION | WC | URINAL | WASH BASIN | TOTAL | COST
CONVENTION CENTER
| Basement 1 | 51 | 44 | 55 | 150 | 3750000
| Basement 2 | 56 | 44 | 28 | 128 | 3200000
| Ground floor | 35 | 26 | 17 | 78 | 1950000
| First floor | 26 | 17 | 12 | 55 | 1375000
| Second floor | 43 | 38 | 31 | 112 | 2800000
| Third floor | 22 | 23 | 26 | 71 | 1775000
| Fourth floor | 18 | 19 | 24 | 61 | 1525000
| Fifth floor | 24 | 17 | 15 | 56 | 1400000
| Sixth floor | 37 | 31 | 54 | 122 | 3050000
| Seventh floor | 5 | 4 | 2 | 11 | 275000
| SUB TOTAL | 317 | 263 | 264 | 844 | 21100000
| EXHIBITION HALL 1 AND FOYER 1 | 171 | 247 | 169 | 587 | 14675000
| SUB TOTAL | 171 | 247 | 169 | 587 | 14675000
| EXHIBITION HALL 2 AND FOYER 2 | 334 | 451 | 317 | 1102 | 27550000
| SUB TOTAL | 334 | 451 | 317 | 1102 | 27550000
GRAND TOTAL | [5 empty] | 63325000
TOTAL WC | [5 empty] | 822
TOTAL URINAL | [5 empty] | 961
TOTAL WASH BASIN | [5 empty] | 750
TOTAL FIXTURE | [5 empty] | 2533

## LL 3 (hidden)
LONG LEAD ITEMS - ECC DWARKA
S.NO | ITEM DESCRIPTION
1 | STRUCTURAL STEEL
2 | ROOFING
3 | SOLAR PV SYSTEM
4 | CABLES HT
5 | VHT
6 | AHU
7 | V Fans
8 | TFA
9 | PHE
10 | CHW Pipes
11 | CHILLER
12 | HEAT PUMPS
13 | TRANSFORMER
14 | COOLING TOWER
15 | HT PANEL
16 | GRID SUB STATION
17 | SOLID WASTE
18 | STP
19 | WTP
20 | RETRACTABLE SEATING
21 | LED ON FAÇADE
22 | SLIDING FOLDING