## Summary
Sr. No. | Item Description | Weighatge for the project
1 | Preliminaries | 1%
2 | Design | 3%
3 | Procurement | 27.5%
4 | Construction | 63.5%
5 | T&C | 5%
| Total | 100%

## General Stages
Stage Payment Statement for General
Sr. No.

## Engineering Stages
Sr. No. | ITEM DESCRIPTION | Price Bid Value INR (Crore) | Engineering Stage
|  |  | Zone | % Breakup Status | Stage Status | No of Stages | Final File for % Breakup | Final File for Stage
1 | Engineering Stages |  | All |  |  |  | Percentage Breakup

## Procurement Stages
Link to Final Working File | PROCUREMENT STAGES
No. of Stages | 355

## Construction Stages
Sr. No. | ITEM DESCRIPTION | Price Bid Value INR (Crore) | Construction Stage
|  |  | Zone | % Breakup Status | Stage Status | No of Stages | Final File for % Breakup | Final File for Stage
| PROJECT TOTAL | 2791 |  |  |  | 8439
A | COST OF BUILDING WORKS (Fully facilitated as per Scope, Design Basis Report, Technical Specifications, Design Intent, Tender Drawings & Tender Documents in complete) | 2050.8484 |  |  |  | 8156
A.01 | Exhibition Hall No. 1 | 340.4401 |  |  |  | 1128
A.01.a | Civil works including structural steel, roofing complete | 145.9615 | Zone-02 | Submitted, Final Review Required | Submitted, Final Review Required | 179 | Structure % Breakup | Structure
A.01.b | Internal Finishing including Acoustics and Special Finishes complete | 83.2149 | Zone-02 | Submitted, Final Review Required | Submitted, Final Review Required | 303 | Internal Finishes | Internal Finish
A.01.c | External Finishes including Façade, Special Finishes | 21.9482 | Zone-02 | Submitted, Final Review Required | Submitted, Final Review Required | 60 | External Finishing Percentage Breakup | External Finishes
A.01.d | Plumbing works | 2.9668 | Zone-02 | Submitted, Final Review Required | Submitted, Final Review Required | 42 | 1.D PHE | PHE
A.01.e | Electrical works | 13.3856 | Zone-02 | Submitted, Final Review Required | Submitted, Final Review Required | 90 | 1.E & 1.J ELECTRICAL | ELECTRICAL
A.01.f | Lift, Escalators & travellators | 3.1926 | Zone-02 | Submitted, Final Review Required | Submitted, Final Review Required | 6 | LIFT ESCALATOR & TRAVELLATOR | VHT
A.01.g | HVAC works | 11.519 | Zone-02 | Submitted, Final Review Required | Submitted, Final Review Required | 54 | 1.G HVAC | HVAC
A.01.h | Firefighting works | 8.64 | Zone-02 | Submitted, Final Review Required | Submitted, Final Review Required | 54 | 1.H FPS | FPS
A.01.i | ICT, AV system, Security & Surveillance | 35.4233 | Zone-02 | Submitted, Final Review Required | File to be merged with Zone-02 File | 340 | Exhibition Hall-01 & Foyer-01 | Zone 2
A.01.j | Lighting | 14.1884 | Zone-02 | Included in 1a | Included in 1a | Included in 1a | 1.E & 1.J ELECTRICAL | ELECTRICAL
A.01.k | Misc. works | 0 | Zone-02 | NA | NA | NA | NA | NA
A.02 | Exhibition Hall No. 2 | 287.4552 |  |  |  | 993
A.02.a | Civil works including structural steel | 138.2892 | Zone-03 | Submitted, Final Review Required | Submitted, Final Review Required | 160 | STRUCTURE % BREAKUP | Structure
A.02.b | Internal Finishing including Acoustics and Special Finishes | 67.2389 | Zone-03 | Submitted, Final Review Required | Submitted, Final Review Required | 282 | Internal Finishes Breakup | Internal Finishes
A.02.c | External Finishes including Façade, Special Finishes | 23.2853 | Zone-03 | Submitted, Final Review Required | Stages in separate Sheet to be combined with other items | 60 | External Finishes | External Finishes Stages
A.02.d | Plumbing works | 2.6618 | Zone-03 | Submitted, Final Review Required | Submitted, Final Review Required | 42 | 2.D PHE | PHE
A.02.e | Electrical works | 12.4811 | Zone-03 | Submitted, Final Review Required | Submitted, Final Review Required | 90 | 2.E & 2.J ELECTRICAL | ELECTRICAL
A.02.f | Lift, Escalators & travellators | 4.3091 | Zone-03 | Submitted, Final Review Required | Submitted, Final Review Required | 6 | LIFT ESCALATOR & TRAVELLATOR | VHT
A.02.g | HVAC works | 13.2824 | Zone-03 | Submitted, Final Review Required | Submitted, Final Review Required | 54 | 2.G HVAC | HVAC
A.02.h | Firefighting works | 6.6906 | Zone-03 | Submitted, Final Review Required | Submitted, Final Review Required | 36 | 2.H FPS | FPS
A.02.i | ICT & AV system | 13.9473 | Zone-03 | Submitted, Final Review Required | File to be merged with Zone-03 File | 263 | Exhibition Hall-02 & Foyer-02 | Zone 3
A.02.j | Lighting | 5.2695 | Zone-03 | Included in 2a | Included in 2a | Included in 2a | 2.E & 2.J ELECTRICAL | Included in 2a
A.02.k | Misc. works | 0 | Zone-03 | NA | NA | NA | NA | NA
A.03 | Foyer including Basement in front of Exhibition Hall No. 1 | 231.7553 |  |  |  | 1089
A.03.a | Civil works including structural steel | 138.6846 | Zone-05 | Submitted, Final Review Required | Submitted, Final Review Required | 195 | Structure Percentage Breakup | Structure
A.03.b | Internal Finishing including Acoustics and Special Finishes | 37.6976 | Zone-05 | Submitted, Final Review Required | Submitted, Final Review Required | 408 | Item wise break-up for Internal Finishes | Internal Finish
A.03.c | External Finishes including Façade, Special Finishes | 17.0755 | Zone-05 | Submitted, Final Review Required | Stages in separate Sheet to be combined with other items | 60 | External Finishes Percentage Breakup | External Finishes Stages
A.03.d | Plumbing works | 0.34857 | Zone-05 | Submitted, Final Review Required | Submitted, Final Review Required | 72 | 3.D PHE | PHE
A.03.e | Electrical works | 6.8707 | Zone-05 | Submitted, Final Review Required | Submitted, Final Review Required | 120 | 3.E & 3.J ELECTRICAL | Electical
A.03.f | Lift, Escalators & travellators | 3.2806 | Zone-05 | Submitted, Final Review Required | Submitted, Final Review Required | 6 | LIFT ESCALATOR & TRAVELLATOR | VHT
A.03.g | HVAC works | 9.2864 | Zone-05 | Submitted, Final Review Required | Submitted, Final Review Required | 72 | 3.G HVAC | HVAC
A.03.h | Firefighting works | 5.8317 | Zone-05 | Submitted, Final Review Required | Submitted, Final Review Required | 72 | 3.H FPS | FPS
A.03.i | ICT & AV system | 10.8733 | Zone-05 | Submitted, Final Review Required | File to be merged with Zone-03 File | 84 | Exhibition Hall-01 & Foyer-01 | Zone 5
A.03.j | Lighting | 1.8062 | Zone-05 | Included in 3a | Included in 3a | Included in 3a | 3.E & 3.J ELECTRICAL | Included in 3a
A.03.k | Misc. works | 0 | Zone-05 | NA | NA | NA | NA | NA
A.04 | Foyer including Basement in front of Exhibition Hall No. 2 | 236.7494 |  |  |  | 1112
A.04.a | Civil works including structural steel | 133.9662 | Zone-06 | Submitted, Final Review Required | Submitted, Final Review Required | 215 | STRUCTURE % BREAKUP | STRUCTURE
A.04.b | Internal Finishing including Acoustics and Special Finishes | 43.6006 | Zone-06 | Submitted, Final Review Required | Submitted, Final Review Required | 531 | Internal Finishes | INTERNAL FINISH
A.04.c | External Finishes including Façade, Special Finishes | 23.977 | Zone-06 | Submitted, Final Review Required | Stages in separate Sheet to be combined with other items | 60 | External Finishes Percentage Breakup | External Finishes Stages
A.04.d | Plumbing works | 0.1002 | Zone-06 | Submitted, Final Review Required | Submitted, Final Review Required | 72 | 2.D PHE | PHE
A.04.e | Electrical works | 7.3204 | Zone-06 | Submitted, Final Review Required | Submitted, Final Review Required | 0 | 2.E & 2.J ELECTRICAL | ELECTRICAL
A.04.f | Lift, Escalators & travellators | 4.7934 | Zone-06 | Submitted, Final Review Required | Submitted, Final Review Required | 6 | LIFT ESCALATOR & TRAVELLATOR | VHT
A.04.g | HVAC works | 10.9201 | Zone-06 | Submitted, Final Review Required | Submitted, Final Review Required | 72 | HVAC WORKS | HVAC
A.04.h | Firefighting works | 6.5677 | Zone-06 | Submitted, Final Review Required | Submitted, Final Review Required | 72 | Firefighting works | FPS
A.04.i | ICT & AV system | 2.4176 | Zone-06 | Submitted, Final Review Required | Percentage Breakup Pending | 84 | Pending | Zone 6
A.04.j | Lighting | 3.0863 | Zone-06 | Included in 4a | Included in 4a | Included in 4a | 2.E & 2.J ELECTRICAL | Included in 4a
A.04.k | Misc. works | 0 | Zone-06 | NA | NA | NA | NA | NA
A.05 | Convention Centre | 654.9368 |  |  |  | 2193
A.05.a | Civil works including structural steel | 209.8451 | Zone-01 | Percentage Breakup not linked with Stage Payment | Completed, % Breakup awaited for Review | 308 | Structure breakup | Structure
A.05.b | Internal Finishing including Acoustics and Special Finishes | 179.5618 | Zone-01 | Submitted, Final Review Required | Completed, % Breakup awaited for Review | 882 | FINISHES PERCENTAGE BREAKUP | Internal Finishes
A.05.c | External Finishes including Façade, Special Finishes | 40.7803 | Zone-01 | Submitted, Final Review Required | Completed, % Breakup awaited for Review | 70 | 0 | External Finishes
A.05.d | Plumbing works | 7.4809 | Zone-01 | Submitted, Final Review Required | Completed, % Breakup awaited for Review | 99 | 5.D PLUMBING WORKS | PHE
A.05.e | Electrical works | 16.3809 | Zone-01 | Submitted, Final Review Required | Completed, % Breakup awaited for Review | 165 | 5.E & 5.J ELECTRICAL | Electrical
A.05.f | Lift, Escalators & travellators | 18.4214 | Zone-01 | Submitted, Final Review Required | Completed, % Breakup awaited for Review | 6 | LIFT ESCALATOR & TRAVELLATOR | VHT
A.05.g | HVAC works | 22.5655 | Zone-01 | Submitted, Final Review Required | Completed, % Breakup awaited for Review | 99 | 5.G HVAC | HVAC
A.05.h | Firefighting works | 8.9055 | Zone-01 | Submitted, Final Review Required | Completed, % Breakup awaited for Review | 99 | 5.H FPS | FPS
A.05.i | ICT & AV system | 119.5615 | Zone-01 | Submitted, Final Review Required | Completed, % Breakup awaited for Review | 465 | ICT Percentage Breakup | ICT
A.05.j | Lighting | 31.4339 | Zone-01 | Submitted, Final Review Required | Completed, % Breakup awaited for Review | Inlcuded | 5.E & 5.J ELECTRICAL | Electrical
A.05.k | Misc. works | 0 | Zone-01 | NA | NA |  | NA | NA
A.06 | Exhibition hall -3 ( basement ) | 113.5269 |  |  |  | 466
A.06.a | Civil works including structural steel | 86.2839 | Zone-04 | To be Reviewed by EE | Completed, % Breakup awaited for Review | 168 | Pending | Structure
A.06.b | Internal Finishing including Acoustics and Special Finishes | 10.4919 | Zone-04 | Percentage Breakup Pending | Plant Room Stages to be made separate. Presently combined | 84 | Pending | Internal Finishes 6B,11B
A.06.c | External Finishes including Façade, Special Finishes | 0.048168 | Zone-04 | Pending by EPCC, % Breakup for CC provided by EE on 18 June 18 | Stages Prepared, but can be revied after Percentage Breakup submission | 0 | Pending | Pending
A.06.d | Plumbing works | 1.4983 | Zone-04 | Percentage Breakup Pending | Stages for Plant Room not Provided | 14 | Pending | PHE
A.06.e | Electrical works | 3.4403 | Zone-04 | Percentage Breakup Pending | Plant Room Stages to be made separate. Presently combined | 90 | Pending | Electrical 6E,6J,11E,11J
A.06.f | Lift, Escalators & travellators | 0 | Zone-04 | NA | NA | 0 | NA | NA
A.06.g | HVAC works | 4.1967 | Zone-04 | Percentage Breakup Pending | Stages Prepared, but can be revied after Percentage Breakup submission | 18 | Pending | HVAC
A.06.h | Firefighting works | 5.0246 | Zone-04 | Percentage Breakup Pending | Stages Prepared, but can be revied after Percentage Breakup submission | 12 | Pending | FPS
A.06.i | ICT & AV system | 1.6793 | Zone-04 | Percentage Breakup Pending | Completed, % Breakup awaited for Review | 80 | Zone 4 | ICT 6I,11I
A.06.j | Lighting | 0.86373 | Zone-04 | Percentage Breakup Pending | Plant Room Stages to be made separate. Presently combined | Included in 6.e | Pending | Included in 6.e
A.06.k | Misc. works | 0 | Zone-04 | NA | NA | NA | NA | NA
A.07 | Basement adjacent to Convention Centre | 59.804 |  |  |  | 572
A.07.a | Civil works including structural steel | 40.6662 | Zone-07 | To be Reviewed by EE | Completed, % Breakup awaited for Review | 104 | Struture Percentage Breakup | STRUCTURE
A.07.b | Internal Finishing including Acoustics and Special Finishes | 2.7912 | Zone-07 | To be Reviewed by EE | Completed, % Breakup awaited for Review | 216 | INTERNAL FINISHES | INTERNAL FINISH
A.07.c | External Finishes including Façade, Special Finishes | 0 | Zone-07 | NA | NA | 0 | NA | NA
A.07.d | Plumbing works | 0.26679 | Zone-07 | Incomplete by EPCC | Completed, % Breakup awaited for Review | 36 | 7.D PLUMBING WORKS | PHE
A.07.e | Electrical works | 4.9814 | Zone-07 | Incomplete by EPCC | Completed, % Breakup awaited for Review | 60 | 7.E & 7.K ELECTRICAL | ELECTRICAL
A.07.f | Lift, Escalators & travellators | 0 | Zone-07 | Incomplete by EPCC | Completed, % Breakup awaited for Review | 0 | LIFT ESCALATOR & TRAVELLATOR
A.07.g | HVAC works | 5.9542 | Zone-07 | Incomplete by EPCC | Completed, % Breakup awaited for Review | 36 | 7.G HVAC | HVAC
A.07.h | Firefighting works | 3.5287 | Zone-07 | Incomplete by EPCC | Completed, % Breakup awaited for Review | 36 | 7.E & 7.K ELECTRICAL | FPS
A.07.i | Pneumatic Solid waste Plant | 0 | Zone-07 | NA | NA | 0 | NA | NA
A.07.j | ICT & AV system | 1.0543 | Zone-07 | Percentage Breakup Pending | Percentage Breakup Pending | 84 | Pending | Zone 7
A.07.k | Lighting | 0.56129 | Zone-07 | Incomplete by EPCC | NA | Included | 7.E & 7.K ELECTRICAL | Included in 7e
A.07.l | Misc. works | 0 | Zone-07 | NA | NA | NA | NA | NA
A.08 | Electrical Substation | 17.5604 |  |  |  | 198
A.08.a | Civil works including structural steel | 6.4045 | Zone-8 ESS 1 & 2 | Percentage Breakup Pending, Reviewed on 7 Jul 18 | Percentage Breakup Pending, Reviewed on 7 Jul 18 | 21 | Pending | Structure
A.08.b | Internal Finishing including Acoustics and Special Finishes | 3.7961 | Zone-8 ESS 1 & 2 | Percentage Breakup Pending, Reviewed on 7 Jul 18 | Percentage Breakup Pending, Reviewed on 7 Jul 18 | 54 | Pending | Finishes
A.08.c | External Finishes including Façade, Special Finishes | 0 | Zone-8 ESS 1 & 2 | NA | NA | NA | NA | NA
A.08.d | Plumbing works | 0.05121 | Zone-8 ESS 1 & 2 | Percentage Breakup Pending, Reviewed on 7 Jul 18 | Percentage Breakup Pending, Reviewed on 7 Jul 18 | 12 | Pending | PHE
A.08.e | Electrical works | 1.3516 | Zone-8 ESS 1 & 2 | Percentage Breakup Pending, Reviewed on 7 Jul 18 | Percentage Breakup Pending, Reviewed on 7 Jul 18 | 20 | Pending | Electrical 8E,8J
A.08.f | Lift, Escalators & travellators | 0 | Zone-8 ESS 1 & 2 | NA | NA | NA | NA | NA
A.08.g | HVAC works | 0.23385 | Zone-8 ESS 1 & 2 | Percentage Breakup Pending, Reviewed on 7 Jul 18 | Percentage Breakup Pending, Reviewed on 7 Jul 18 | 18 | Pending | HVAC
A.08.h | Firefighting works | 0.4214 | Zone-8 ESS 1 & 2 | Percentage Breakup Pending, Reviewed on 7 Jul 18 | Percentage Breakup Pending, Reviewed on 7 Jul 18 | 12 | Pending | FPS
A.08.i | ICT & AV system | 0.26847 | Zone-8 ESS 1 & 2 | Percentage Breakup Pending, Reviewed on 7 Jul 18 | Percentage Breakup Pending, Reviewed on 7 Jul 18 | 61 | Pending | ICT
A.08.j | Lighting | 0.14764 | Zone-8 ESS 1 & 2 | Percentage Breakup Pending, Reviewed on 7 Jul 18 | Percentage Breakup Pending, Reviewed on 7 Jul 18 | Included in 8e | Pending | Included in 8e
A.08.k | Transformers | 4.8856 | Zone-8 ESS 1 & 2 | Percentage Breakup Pending, Reviewed on 7 Jul 18 | Percentage Breakup Pending, Reviewed on 7 Jul 18 | 0 | Pending | Transformer 8k
A.08.l | Misc. works | 0 | Zone-8 ESS 1 & 2 | NA | NA | NA | NA | NA
A.09 | DG Building | 70.1606 |  |  |  | 194
A.09.a | Civil works including structural steel | 20.834 | Zone-8 DG Building | Percentage Breakup Pending, Reviewed on 7 Jul 18 | Percentage Breakup Pending, Reviewed on 7 Jul 18 | 78 | Pending | Structure
A.09.b | Internal Finishing including Acoustics and Special Finishes | 4.548 | Zone-8 DG Building | Percentage Breakup Pending, Reviewed on 7 Jul 18 | Percentage Breakup Pending, Reviewed on 7 Jul 18 | 36 | Pending | Finishes
A.09.c | External Finishes including Façade, Special Finishes | 1.8243 | Zone-8 DG Building | Percentage Breakup Pending, Reviewed on 7 Jul 18 | Percentage Breakup Pending, Reviewed on 7 Jul 18 | 10 | Pending | External Finishes
A.09.d | Plumbing works | 0.12952 | Zone-8 DG Building | Percentage Breakup Pending, Reviewed on 7 Jul 18 | Percentage Breakup Pending, Reviewed on 7 Jul 18 | 18 | Pending | PHE
A.09.e | Electrical works | 5.8023 | Zone-8 DG Building | Percentage Breakup Pending, Reviewed on 7 Jul 18 | Percentage Breakup Pending, Reviewed on 7 Jul 18 | 20 | Pending | Electrical
A.09.f | Lift, Escalators & travellators | 0 | Zone-8 DG Building | NA | NA | NA | NA | NA
A.09.g | HVAC works | 3.6937 | Zone-8 DG Building | Percentage Breakup Pending, Reviewed on 7 Jul 18 | Percentage Breakup Pending, Reviewed on 7 Jul 18 | 12 | Pending | HVAC
A.09.h | Firefighting works | 0.37134 | Zone-8 DG Building | Percentage Breakup Pending, Reviewed on 7 Jul 18 | Percentage Breakup Pending, Reviewed on 7 Jul 18 | 12 | Pending | FPS
A.09.i | ICT & AV system | 0 | Zone-8 DG Building | NA | NA | NA | NA | NA
A.09.j | Lighting | 0.29809 | Zone-8 DG Building | Percentage Breakup Pending, Reviewed on 7 Jul 18 | Percentage Breakup Pending, Reviewed on 7 Jul 18 | Included in a.9.e | Pending
A.09.k | Diesel Generators | 31.1383 | Zone-8 DG Building | Percentage Breakup Pending, Reviewed on 7 Jul 18 | Percentage Breakup Pending, Reviewed on 7 Jul 18 | 8 | Pending | Electrical High Side 9K,Part B 3 9K,Part B 3 9K,Part B 3 9K,Part B 3 9K,Part B 3 9K,Part B 3 9K,Part B 3 9K,Part B 3
A.09.l | Cooling Towers | 1.521 | Zone-8 DG Building | Percentage Breakup Pending, Reviewed on 7 Jul 18 | Percentage Breakup Pending, Reviewed on 7 Jul 18 | 0 | Pending | Pending
A.09.m | Misc. works | 0 | Zone-8 DG Building | NA | NA | NA | NA | NA
A.10 | Fire Station & Disaster Management Building including Medical Centre | 3.4181 |  |  |  | 181
A.10.a | Civil works including structural steel | 1.3984 | Zone-8 Fire Station | Percentage Breakup Pending, Reviewed on 7 Jul 18 | Percentage Breakup Pending, Reviewed on 7 Jul 18 | 21 | Pending | Structure
A.10.b | Internal Finishing including Acoustics and Special Finishes | 0.97021 | Zone-8 Fire Station | Percentage Breakup Pending, Reviewed on 7 Jul 18 | Percentage Breakup Pending, Reviewed on 7 Jul 18 | 84 | Pending | Internal Finishes
A.10.c | External Finishes including Façade, Special Finishes | 0 | Zone-8 Fire Station | NA | NA | NA | NA | NA
A.10.d | Plumbing works | 0.072351 | Zone-8 Fire Station | Percentage Breakup Pending, Reviewed on 7 Jul 18 | Percentage Breakup Pending, Reviewed on 7 Jul 18 | 12 | Pending | PHE
A.10.e | Electrical works | 0.43127 | Zone-8 Fire Station | Percentage Breakup Pending, Reviewed on 7 Jul 18 | Percentage Breakup Pending, Reviewed on 7 Jul 18 | 40 | Pending | Electrical 10E,10J
A.10.f | Lift, Escalators & travellators | 0 | Zone-8 Fire Station | NA | NA | NA | NA | NA
A.10.g | HVAC works | 0 | Zone-8 Fire Station | NA | NA | NA | NA | NA
A.10.h | Firefighting works | 0.075579 | Zone-8 Fire Station | Percentage Breakup Pending, Reviewed on 7 Jul 18 | Percentage Breakup Pending, Reviewed on 7 Jul 18 | 24 | Pending | FPS
A.10.i | ICT & AV system | 0 | Zone-8 Fire Station | NA | NA | NA | NA | NA
A.10.j | Lighting | 0.47031 | Zone-8 Fire Station | Percentage Breakup Pending, Reviewed on 7 Jul 18 | Percentage Breakup Pending | Included in 10.e | Pending | Included in 10.e
A.10.k | Misc. works | 0 | Zone-8 Fire Station | NA | NA |  |  | NA
A.11 | Plant Room & Service Gallery | 35.0413 |  |  |  | 30
A.11.a | Civil works including structural steel | 0 | Zone-04 | NA | NA | NA | NA | NA
A.11.b | Internal Finishing including Acoustics and Special Finishes | 3.1972 | Zone-04 | Percentage Breakup Pending, Reviewed on 7 Jul 18 | Plant Room Stages to be made separate. Presently combined | Included in 6b | Pending | Internal Finishes 6B,11B
A.11.c | External Finishes including Façade, Special Finishes | 0 | Zone-04 | NA | NA | NA | NA | NA
A.11.d | Plumbing works | 0.089814 | Zone-04 | Percentage Breakup Pending, Reviewed on 7 Jul 18 | Stages can be reviewed after Percentage Breakup | 5 | Pending | PHE Plant Room
A.11.e | Electrical works | 2.7189 | Zone-04 | Percentage Breakup Pending, Reviewed on 7 Jul 18 | Plant Room Stages to be made separate. Presently combined | Included in 6e | Pending | Electrical 6E,6J,11E,11J
A.11.f | Lift, Escalators & travellators | 0 | Zone-04 | NA | NA | NA | NA | NA
A.11.g | HVAC works | 25.539 | Zone-04 | Percentage Breakup Pending, Reviewed on 7 Jul 18 | Stages can be reviewed after Percentage Breakup | 19 | Pending | A/C Plant Room
A.11.h | Firefighting works | 2.5231 | Zone-04 | Percentage Breakup Pending, Reviewed on 7 Jul 18 | Stages included in EH3 but not provided | 6 | Pending | Fire Pump Room
A.11.i | ICT & AV system | 0.6436 | Zone-04 | Percentage Breakup Pending, Reviewed on 7 Jul 18 | Completed, % Breakup awaited for Review | Included in 6i | Zone 4 | ICT 6I,11I
A.11.j | Lighting | 0.32974 | Zone-04 | Percentage Breakup Pending, Reviewed on 7 Jul 18 | Pending by EPCC
A.11.k | Misc. works | 0 | Zone-04 | NA | NA |  |  | NA
B | PART-B: COST OF INFRASTRUCTURE | 398.16 |  |  |  | 240
B.01 | Service Gallery | 98.7237 |  |  |  | 240
B.01.a | Civil works including structural steel | 86.4183 | Zone-08 (SG) | Percentage Breakup Pending, Reviewed on 7 Jul 18 | As per Price Bid B & C it is fully in Zone 8 than why Bid reference says part | 80 | INTERNAL FINISHES | Structure Part 1A
B.01.b | Finishes | 0 | Zone-08 (SG) | NA | NA | NA | NA | NA
B.01.c | Plumbing works | 4.4661 | Zone-08 (SG) | Percentage Breakup Pending, Reviewed on 7 Jul 18 | As per Price Bid B & C it is fully in Zone 8 than why Bid reference says part | 30 | 7.D PLUMBING WORKS | PHE Part B1C,Part B5
B.01.d | HSD Distribution line | 0 | Zone-08 (SG) | NA | NA | NA | NA | NA
B.01.e | PNG line | 0 | Zone-08 (SG) | NA | NA | NA | NA | NA
B.01.f | Electrical works | 1.4139 | Zone-08 (SG) | Percentage Breakup Pending, Reviewed on 7 Jul 18 | As per Price Bid B & C it is fully in Zone 8 than why Bid reference says part | 20 | 7.G HVAC | Electrical Part B1F,Part B3(35%)
B.01.g | HVAC works | 0.87071 | Zone-08 (SG) | Percentage Breakup Pending, Reviewed on 7 Jul 18 | As per Price Bid B & C it is fully in Zone 8 than why Bid reference says part | 10 | 7.E & 7.K ELECTRICAL | HVAC Part B1G,Part B4
B.01.h | Firefighting works | 2.2621 | Zone-08 (SG) | Percentage Breakup Pending, Reviewed on 7 Jul 18 | As per Price Bid B & C it is fully in Zone 8 than why Bid reference says part | 10 | NA | FPS Part B1H,Part B6
B.01.i | Solid Waste pipe Network | 1.5405 | Zone-08 (SG) | Percentage Breakup Pending, Reviewed on 7 Jul 18 | As per Price Bid B & C it is fully in Zone 8 than why Bid reference says part | 10 | Pending | Solid Waste Piping Network Part B1I,Part B9(50%),Part B10(50%)
B.01.j | ICT & AV system | 1.7522 | Zone-08 (SG) | Percentage Breakup Pending, Reviewed on 7 Jul 18 | As per Price Bid B & C it is fully in Zone 8 than why Bid reference says part | 80 | 7.E & 7.K ELECTRICAL | ICT Part B1J
B.01.k | Lighting | 0 | Zone-08 (SG) | NA | NA | NA |  | NA
B.01.l | Misc. works | 0 | Zone-08 (SG) | NA | NA | NA |  | NA
B.02 | Central Control & Command Centre | 0 | Zone-01 to Zone-08 | NA | NA | NA |  | NA
B.03 | Electrical Equipment (High Side) including Cabling upto the buildings | 27.0493 | Zone-01 to Zone-08 | Percentage Breakup Pending | Pending by EPCC |  | Electrical Equipment (High Side) including Cabling upto the buildings
B.04 | HVAC Equipments (High Side) including chilled Water, hot Water and condenser Piping upto the buildings | 21.3364 | Zone-01 to Zone-08 | Percentage Breakup Pending | Pending by EPCC |  | HVAC Equipments (High Side) including chilled Water, hot Water and condenser Piping upto the buildings
B.05 | External Plumbing and Mechanical Equipment including Piping upto the buildings and within complex | 0.50266 | Zone-01 to Zone-08 | Percentage Breakup Pending | Pending by EPCC |  | External Plumbing and Mechanical Equipment including Piping upto the buildings and within complex |  | B.03, B.04, B.05, B.06, B.07, B.08, B.09, B.10, B.11, B.12, B.13
B.06 | External Fire-fighting and Mechanical Equipment including Piping upto the buildings and within complex and Yard Hydrants for the whole complex | 0 | NA | NA | NA |  |  | NA
B.07 | External Sewage System upto the STP | 3.9516 | Zone-08 | Percentage Breakup Pending | Pending by EPCC |  | External Sewage System upto the STP
B.08 | External Storm Water drainage including Rain Water Harvesting System | 15.9154 | Zone-09 | Percentage Breakup Pending | Pending by EPCC |  | External Storm Water drainage including Rain Water Harvesting System
B.09 | Pneumatic Solid Waste Management system including inlets and piping, | 11.851 | Zone-08, Zone-09 | Percentage Breakup Pending | Pending by EPCC |  | Pneumatic Solid Waste Management system including inlets and piping,
B.10 | Solid Waste Plant and Compost Plant including Transport Vehicles, | 4.0931 | Zone-04 | Percentage Breakup Pending | Pending by EPCC |  | Solid Waste Plant and Compost Plant including Transport Vehicles,
B.11 | STP and Pumps | 7.5953 | Zone-04 | Percentage Breakup Pending | Pending by EPCC |  | Pending | Solid Waste Treatment Plant Part B11,Part B10(50%)
B.12 | WTP and Pumps | 0.37947 | Zone-04 | Percentage Breakup Pending | Pending by EPCC |  | Pending | Water Treatment Plant Part B12
B.13 | Landscaping | 79.5898 |  |  |  | 0
B.13.a | Softscape & Hard scape, Horticulture | 53.3133 | Zone-09 | Percentage Breakup Pending | Pending by EPCC |  | Softscape & Hard scape, Horticulture
B.13.b | Irrigation & drainage | 3.4024 | Zone-09 | Percentage Breakup Pending | Pending by EPCC |  | Irrigation & drainage
B.13.c | water bodies, Fountain | 15.1201 | Zone-09 | Percentage Breakup Pending | Pending by EPCC |  | water bodies, Fountain
B.13.d | Plazas, Pergolas & Canopies | 3.8667 | Zone-09 | Percentage Breakup Pending | Pending by EPCC |  | Plazas, Pergolas & Canopies
B.13.e | Street Furniture | 3.8874 | Zone-09 | Percentage Breakup Pending | Pending by EPCC |  | Street Furniture
B.14 | Pathways & Walkway | 12.8206 | Zone-09 | Percentage Breakup Pending | Pending by EPCC |  | Pathways & Walkway
B.15 | Open Exhibition Area | 0 | NA | Percentage Breakup Pending | Pending by EPCC |  | Open Exhibition Area
B.16 | Roads, Ramps, Tunnels | 97.4606 | Zone-02, Zone-09 | Percentage Breakup Pending | Pending by EPCC |  | Roads, Ramps, Tunnels
B.17 | External area Lighting | 16.8912 | Zone-09 | Percentage Breakup Pending | Pending by EPCC |  | External area Lighting
C | Part-C: Cost of Specialised Works | 341.9916 |  |  |  | 43
C.01 | Retractable seating (Automatic) | 171.9875 |  |  |  | 10
C.01.a | Convention Centre | 150.3515 | Zone-01 | Percentage Breakup Pending | Stage Description not OK and does not identify the works | 5 |  | Convention Centre
C.01.b | Exhibition Hall | 21.636 | Zone-02 | Percentage Breakup Pending | Stage Description not OK and does not identify the works | 5 |  | Exhibition Hall-01
C.02 | LED on External Facade | 139.968 | Zone-01, Zone-02 & Zone-03 | Percentage Breakup Pending | Stage Description not OK and does not identify the works | 33 |  | Convention Centre
C.03 | Sliding folding / Vertical Partitions (Automatic) | 25.3705
C.03.a | Sliding/Folding Acoustic Partitions. | 5.4144 | Zone-01 | Percentage Breakup Pending | Percentage Breakup Pending | 5
C.03.b | Vertically Retractable Non Acoustic, Partitions | 19.9561 | Zone-01 | Percentage Breakup Pending | Percentage Breakup Pending | 5
C.04 | Internal / External Signage | 4.6656 | Zone-09 | Percentage Breakup Pending | Zone-09, Pending | 0

## Testing & Commissioning Stages
Percentage breakup to be provided